## Slide 1
BRAVE BLOSSOM
Capital Schedule Review & Assessment
Source:
Complex_Valuation_Model_-_Team_Green_1.xlsx
Key Finding: New schedule is +$74.4M more expensive in PV terms despite only +$3.6M nominal difference — driven by front-loading
Estimated NPV impact: $997M → ~$923M (-7.5%)
September 2026

## Slide 2
Executive Summary
Headline Metrics
Brave Blossom Capital Review
2
Line Items
24
Old: 12
+12
Equipment-level granularity
Nominal Subtotal
$521.2M
Old: $518.4M
+$2.8M
+0.5% — nearly identical
PV of Capex (w/ cont.)
$518.2M
Old: $443.8M
+$74.4M
+16.8% — front-loading penalty
Peak Year
Y1: $132.1M
Old: Y6: $221.5M
Shifted fwd
From Y6 to Y1
Critical Finding The new schedule is nearly identical nominally (+$2.8M, +0.5%) but $74.4M more expensive in present-value terms (+16.8%). This divergence is driven entirely by front-loading: $132.1M deployed in Year 1 vs $10M in the old schedule. The old schedule peaked in Year 6 ($221.5M for the longwall package), which discounted heavily over 6.5 years.

## Slide 3
Structural Overview
Old vs New Capital Approach
Brave Blossom Capital Review
3
OLD SCHEDULE (Populated)
▪ 12 project-level / phase-based line items
▪ Longwall = $190M single line item
▪ Mining Equipment = $69.9M single line
▪ Infrastructure + CHPP EPCM = $48M lump
▪ 7 active years (Y1–Y7, 2027–2033)
▪ Peak: Year 6 — $221.5M (longwall package)
▪ Back-loaded: only $26M in Y1–Y2 (3.9%)
▪ No cached formula values (never opened in Excel)
NEW SCHEDULE (Team Green)
▪ 24 equipment-level / unit-based line items
▪ Longwall decomposed: Shearer $11M, AFC $6M, BSL $6M, Roof Supports $300M
▪ Continuous Miners: 3 units × $9M = $27M
▪ CHPP broken out: Repairs $5M, Conveyor $5M, Bin $9M
▪ 8 active years (Y1–Y8, 2027–2034)
▪ Peak: Year 1 — $132.1M (front-loaded)
▪ Front-loaded: $294.6M in Y1–Y2 (43.5%)
▪ Cached formula values present (opened in Excel)

## Slide 4
Year-by-Year Capital Profile
New vs Old — Total w/ Contingency (AUDM)
Brave Blossom Capital Review
4
Chart: 
| Y1 2027 | Y2 2028 | Y3 2029 | Y4 2030 | Y5 2031 | Y6 2032 | Y7 2033 | Y8 2034
New (Team Green) | 171.67 | 122.92 | 108.94 | 107.64 | 82.88 | 77.03 | 3.25 | 3.25
Old (Populated) | 13 | 13 | 76.7 | 109.2 | 142.87 | 287.95 | 31.2 | 0
FRONT-LOADING
New Y1–Y2: $294.6M (43.5%) Old Y1–Y2: $26.0M (3.9%) $268.6M shifted forward by 4–5 years
TOTALS (w/ Contingency)
 | New | Old | Delta
Base | $521.2M | $518.4M | +$2.8M
w/ 30% Cont. | $677.6M | $673.9M | +$3.6M
New peak: Y1 ($171.7M w/ cont.) — ventilation, roof supports, miners, substations deploy simultaneously.
Old peak: Y6 ($288.0M w/ cont.) — longwall package + mining equipment + infrastructure concentrated.

## Slide 5
Present-Value Analysis
8% Discount Rate, Mid-Year Convention, Base Year 2026
Brave Blossom Capital Review
5
Chart: 
| Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8
New PV (AUDM) | 158.78 | 105.23 | 86.36 | 79.01 | 56.33 | 48.48 | 1.89 | 1.75
Old PV (AUDM) | 12.02 | 11.13 | 60.81 | 80.15 | 97.11 | 181.21 | 18.18 | 0
PV DELTA
+$74.4M
New PV ($518.2M) vs Old PV ($443.8M)
+16.8% despite only +0.5% nominal
NOMINAL vs PV DIVERGENCE
 | Nominal | PV (8%)
New (w/ cont.) | $677.6M | $518.2M
Old (w/ cont.) | $673.9M | $443.8M
Delta | +$3.6M (+0.5%) | +$74.4M (+16.8%)
The classic "front-loading penalty": capital brought forward costs more in PV terms even at equal nominal amounts. Old Y6 longwall ($221.5M) discounts to $139.5M; new Y1–Y2 capital ($226.6M) discounts to $205.8M — a $66.3M PV difference from timing alone.

## Slide 6
Top-5 Cost Drivers
New Schedule — % of Base Capital
Brave Blossom Capital Review
6
Chart: 
| Roof Supports (×300) | Continuous Miners (×3) | Ventilation Network | Pump Infrastructure | Geo Studies (×3)
Cost (AUDM) | 300 | 27 | 20 | 20 | 15
ROOF SUPPORTS
57.6%
of all base capital
300 units × $1,000k = $300M
Larger than the entire old longwall package ($190M)
This single item drives the entire NPV delta
OLD SCHEDULE — TOP-5
1. Longwall | $190.0M | 36.7%
2. Mining Equipment | $69.9M | 13.5%
3. Infra + CHPP EPCM | $48.0M | 9.3%
4. Ventilation Shafts | $40.0M | 7.7%
5. UG Conveyors Reuse | $40.0M | 7.7%

## Slide 7
New Capital Schedule
24 Equipment-Level Line Items
Brave Blossom Capital Review
7
# | Item | Unit Cost (A$k) | Units | Total (A$M) | % Base | Years
1 | Shearer | 11,000 | 1.00 | 11.00 | 2.1% | Y1–Y4
2 | CHPP Structural Repairs | 5,000 | 1.00 | 5.00 | 1.0% | Y2–Y3
3 | CHPP Conveyor | 5,000 | 1.00 | 5.00 | 1.0% | Y4–Y5
4 | CHPP Raw Coal Bin | 9,000 | 1.00 | 9.00 | 1.7% | Y3–Y6
5 | Ventilation Network | 20,000 | 1.00 | 20.00 | 3.8% | Y1
6 | Gas Drainage | 12,000 | 1.00 | 12.00 | 2.3% | Y1–Y2
7 | ×3 Continuous Miners | 9,000 | 3.00 | 27.00 | 5.2% | Y1–Y6
8 | ×300 Roof Supports | 1,000 | 300.00 | 300.00 | 57.6% | Y1–Y6
9 | ×10 DCBs | 1,000 | 10.00 | 10.00 | 1.9% | Y1–Y5
10 | ×4 U/G Substations | 3,000 | 4.00 | 12.00 | 2.3% | Y1–Y4
11 | ×10 HT Cables | 1,000 | 10.00 | 10.00 | 1.9% | Y1–Y4
12 | AFC (Panline & Chain) | 6,000 | 1.00 | 6.00 | 1.2% | Y1
13 | BSL | 6,000 | 1.00 | 6.00 | 1.2% | Y1
14 | Drift | 12,000 | 1.00 | 12.00 | 2.3% | Y1–Y4
15 | ×4 Shuttle Cars | 1,000 | 4.00 | 4.00 | 0.8% | Y1–Y4
16 | ×2 Breaker Feeder | 2,000 | 2.00 | 4.00 | 0.8% | Y1–Y2
17 | ×12 Driftrunners | 300 | 12.00 | 3.60 | 0.7% | Y1–Y4
18 | ROM Stockpile | 5,000 | 1.00 | 5.00 | 1.0% | Y1–Y2
19 | ×8 Jugs | 700 | 8.00 | 5.60 | 1.1% | Y1–Y4
20 | Pump Infrastructure | 20,000 | 1.00 | 20.00 | 3.8% | Y1–Y8
21 | Monorail | 10,000 | 1.00 | 10.00 | 1.9% | Y1–Y4
22 | ×4 Mobile Fans | 1,000 | 4.00 | 4.00 | 0.8% | Y1–Y4
23 | Geo Studies | 5,000 | 3.00 | 15.00 | 2.9% | Y1–Y4
24 | Exploration Drilling | 5,000 | 1.00 | 5.00 | 1.0% | Y1
 | SUBTOTAL |  |  | 521.20 | 100% | 
 | Contingency (30%) |  |  | 156.36 |  | 
 | TOTAL |  |  | 677.56 |  | 

## Slide 8
Analytical Assessment
Strengths vs Concerns
Brave Blossom Capital Review
8
✓ STRENGTHS
Granularity
24 equipment-level items provide far better visibility than 12 project-level buckets. Correct granularity for pre-feasibility capital estimate.
Phasing Realism
Fractional phasing (0.25/yr, 0.5/yr, 0.125/yr) reflects staged mine development and quarterly deployment rather than single mega-purchases.
Longwall Decomposition
Old $190M longwall broken into shearer ($11M), AFC ($6M), BSL ($6M), roof supports ($300M). More defensible at component level.
Exploration Included
Geo Studies ($15M) + Exploration Drilling ($5M) present, addressing a gap noted in earlier reviews.
CHPP Component Visibility
Three separate CHPP items (repairs, conveyor, bin) totaling $19M — better than old implicit $48M lump.
Cached Values Present
Workbook opened/saved in Excel with cached formula values. All figures cross-verified by independent recomputation.
⚠ CONCERNS
Roof Support Cost — CRITICAL
300 × $1M = $300M (57.6%). Typical shields are $200k–$500k/unit; $1M is top of range. Single most sensitive assumption. Drives entire NPV delta.
Longwall Components Exceed Old
New components total $323M vs old $190M package — 70% more. Either old underpriced roof supports, or new overprices them.
Front-Loading Risk — MATERIAL
$294.6M in Y1–Y2 (43.5%) vs old $26.0M (3.9%). Capital at risk if mine still in pre-production. Creates financing pressure before revenue.
Missing Development Capital
Drift conveyor ($17M), UG conveyors relocation ($20M), mine infrastructure ($5M) = $42M from old schedule with no direct equivalent in new.
Mining Equipment Reduction
Old $69.9M → new ~$21.2M ($48.7M reduction). Confirm scope definition change, not omission.

## Slide 9
NPV Impact
Effect on Brave Blossom Project Valuation
Brave Blossom Capital Review
9
PREVIOUS NPV
$997M
Corrected Brave Blossom NPV (old capital schedule)
→
ESTIMATED NEW NPV
~$923M
With new Team Green capital schedule
-$74.4M (-7.5%)
ASSUMPTIONS & CAVEATS
• Revenue and operating cost schedules assumed unchanged. If new equipment implies different production profiles (CM development + longwall production dual-method), revenue side would also shift.
• PV capital increase (w/ contingency): +$74.4M — the sole driver of the NPV reduction.
• If missing development capital (~$42M nominal, ~$35M PV) is added back, NPV would decrease further to ~$888M.

## Slide 10
Recommendations
Actions Before Incorporation
Brave Blossom Capital Review
10
1
Verify Roof Support Unit Cost
Sense-check $1,000k/unit against supplier quotes. Test $500k, $750k, $1,000k sensitivity. At $500k/unit, schedule drops to $371.2M base — cheaper than old.
CRITICAL
2
Confirm Missing Development Capital
Drift conveyor ($17M), UG conveyors relocation ($20M), mine infrastructure ($5M) — confirm captured elsewhere or genuinely omitted. If omitted, add ~$42M.
HIGH
3
Validate Mining Equipment Scope
Old $69.9M → new ~$21.2M ($48.7M reduction). Confirm this is a scope definition change, not an omission of equipment categories.
HIGH
4
Confirm Production Method
Schedule includes CMs (development) + longwall (production). Confirm dual-method mine. Revenue schedule should reflect both phases.
MEDIUM
5
Evaluate Front-Loading Re-phasing
Moving $50M of roof supports from Y1–Y2 to Y3–Y4 saves ~$8M PV. Evaluate whether 50/yr deployment is a hard constraint or can be optimized.
MEDIUM
For revised analysis: Adopt new schedule as primary basis → Flag roof support cost as #1 sensitivity → Re-compute NPV (~$923M) → Re-examine revenue side for dual-method consistency → Consider adding back missing development items → Update Option A walkthrough & analysis docs

## Slide 11
Summary
New schedule is more defensible
24 equipment-level items vs 12 project-level buckets — correct granularity for pre-feasibility
But $74.4M more expensive in PV
Front-loading penalty: 43.5% of capital in Y1–Y2 vs 3.9% in old schedule
Roof supports are the critical assumption
$300M (57.6% of base) — drives entire NPV delta. Must sense-check unit cost
NPV drops from $997M to ~$923M
7.5% reduction, assuming unchanged revenue and opex
Five verification items before incorporation
Roof support cost, missing capital, equipment scope, production method, re-phasing
Ready for incorporation into revised analysis