## High Level Summary
Item Number | Estimated Cost 2024 Triennial Review
Domain 1 - Surface Infrastructure | 74443157.5538
Domain 2 - Tailings and Reject Emplacement Areas | 126403008.3686
Domain 3 - Overburden / Waste Emplacement Areas | 26410703.8895
Domain 4 - Active Mining, Pits and Voids | 216537686.3034
Domain 5 - Water Management | 5720137.523
Domain 6 - Existing Rehabilitation Areas | 23229568.3761
Domain 7 - Offset Areas | 0
Domain 8 - Underground Mining Areas | 18102519.6934
Domain 9 - Other Lands | 1137592.008
Whole of Site - Sundry Items and HR/Admin/Stakeholders | 2130821.2977
Contingencies etc | 172940318.2547
Holding Costs | 232944486.7318
Total | 900000000

## Planned Closure Detail
Springbok Creek | Planned Closure Costing (2024) |  |  |  | Total Liability | 2024-09-01
900000000
Item Number | Activity / Description | 2024 Quantity | Unit | Cost code | 2024 Unit Rate | Estimated Cost 2024 Triennial Review | 2024 Comments
Domain 1 - Surface Infrastructure | [5 empty] | 74443157.5538
Domain 1A - MIA (Admin, workshops, bathhouse, car park etc) | [5 empty] | 5591103.465
Termination of Services and Demolition Works | [5 empty] | 4487897.2904
1.001 | Disconnect and terminate all services (Water, electricity, gas etc. at point of attachment to site). | 1 | @ | 1.01 | 47518.4566 | 47518.4566 | No change in quantity in 2024 review. A provisional amount used to allow for the removal of services.
1.002 | Demolish and remove small buildings/tanks (admin buildings - single story etc). | 12531.0992 | m2 | 1.09 | 91.3599 | 1144840.1316 | No change in quantity in 2024 review.
1.003 | Remove concrete pads and footings (< 0.3 m thickness) from small buildings and dumping in void. | 13784.2091 | m2 | 1.43 | 41.116 | 566752.0135 | No change in quantity in 2024 review. Estimate includes additional 10% for aprons, pathways etc.
1.004 | Demolish and remove medium buildings | 14731.5454 | m2/level | 1.1 | 92.2979 | 1359690.1838 | No change in quantity in 2024 review. Areas calculated for medium buildings in domain.
1.005 | Remove concrete pads and footings (> 0.3 m thickness) from medium buildings and dumping in void. | 16205.2018 | m2 | 1.44 | 84.485 | 1369096.5049 | No change in quantity in 2024 review. Estimate includes additional 10% for aprons, pathways etc.
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 982125.6465
1.006 | Remove hardstand material (spillage or otherwise) from footprint of Domain (Does not include product stockpiles, CHPP or ROM) (haul distance > 1 km but < 2 km). | 171335.1507 | m3 | 3.08 | 5.7322 | 982125.6465 | No change in quantity in 2024 review. Assume 0.3 m depth hardstand material removed.
Contaminated materials |  | 0 |  |  |  | 121080.5281
1.007 | Onsite remediation of hydrocarbon contaminated soils (>1000m3) | 1003.8532 | m3 | 4.12 | 84.485 | 84810.5374 | No change in quantity in 2024 review. Provisional sum.
1.008 | Construct and set up bioremediation pad | 0.9333 | allow | 4.09a | 38862.2589 | 36269.9907 | No change in quantity in 2024 review.
Domain 1B - CHPP Main Plant |  | 0 |  |  |  | 17123863.9514
Termination of Services and Demolition Works |  | 0 |  |  |  | 0
1.009 | Demolish and remove CHPP | 0.9333 | @ | SS | 18347731 | 17123863.9514
1.01 | Demolish and remove CHPP (include the area of each floor of the structure) | 0 | m2/level | 1.12 | 247.8264 | 0 | Captured above
1.011 | Demolish and remove heavy industrial buildings - crushers, sizing stations, rotary breakers, etc (area of each floor of the structure). | 0 | m2/level | 1.13 | 253.455 | 0 | Captured above
1.012 | Remove concrete pads and footings (> 0.3 m thickness) and dumping in void. | 0 | m2 | 1.44 | 84.485 | 0 | Captured above
Domain 1C - CHPP MOD 4 |  | 0 |  |  |  | 838423.3463
Termination of Services and Demolition Works |  | 0 |  |  |  | 838423.3463
1.013 | Demolish and remove CHPP (include the area of each floor of the structure) | 3147.0797 | m2/level | 1.12 | 247.8264 | 779929.5187 | No change in quantity in 2024 review. ~627 m2 x 5 levels.
1.014 | Remove concrete pads and footings (> 300 mm thickness) and dumping in void. | 692.3575 | m2 | 1.44 | 84.485 | 58493.8276 | No change in quantity in 2024 review. Estimate includes additional 10% for aprons, pathways etc.
Domain 1D - Product Stockpiles and ROM (includes relevant Rail Loop infrastructure) |  | 0 |  |  |  | 13036272.0217
Termination of Services and Demolition Works |  | 0 |  |  |  | 11698301.6237
1.015 | Demolish and remove bucket wheel stacker/reclaimer | 3.7332 | @ | 1.15 | 2252933.3776 | 8410614.8384 | No change in quantity in 2024 review. Just removal of the bucket wheel stacker/reclaim unit - does not include terminate services, remove rails and ballast etc.
1.016 | Demolish and remove on ground conveyors, transfer stations & gantries (scrap only – does not include dismantling for reuse at another site). | 6392.8681 | m | 1.21 | 225.6427 | 1442504.1969 | No change in quantity in 2024 review. All within the CHPP/stockpile area.
1.017 | Demolish and remove elevated conveyors, transfer stations & gantries (scrap only – does not include dismantling for reuse at another site). | 355.1593 | m | 1.22 | 463.0575 | 164459.199 | No change in quantity in 2024 review. All within the CHPP/stockpile area.
1.018 | Demolish and remove overhead conveyors, transfer stations & gantries (scrap only – does not include dismantling for reuse at another site) | 355.1593 | m | 1.23 | 957.4967 | 340063.8901 | No change in quantity in 2024 review. All within the CHPP/stockpile area.
1.019 | Demolish reclaim tunnel, cut reo and expose reclaim conveyor, then collapse into the reclaim tunnel void (Does not include excavation to expose reclaim tunnel, removal of conveyor or backfilling void). | 11293.3482 | m2 | 1.24 | 107.0143 | 1208550.1576 | No change in quantity in 2024 review.
1.02 | Remove and demolish conveyor from reclaim tunnel (Does not include excavation and demolition of reclaim tunnel roof). | 150.578 | m | 1.25 | 168.97 | 25443.1612 | No change in quantity in 2024 review. Estimate for underground conveyor infrastructure to be removed.
1.021 | Remove concrete pads and footings (> 300 mm thickness) and dumping in void. | 401.5413 | m2 | 1.44 | 84.485 | 33924.215 | No change in quantity in 2024 review. Assume ~0.5 m footings.
1.022 | Demolish and remove rejects bin | 0.9333 | @ | 1.19 | 77940.9378 | 72741.9654 | No change in quantity in 2024 review. Assumes 1250 t coal bin.
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
1.023 | Unsealed roads / vehicle park-up areas – Minor earthworks, final trim and deep rip and seed (pasture grass) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the infrastructure domain.
Contaminated materials |  | 0 |  |  |  | 1327472.7071
1.024 | Remove carbonaceous material (spillage or otherwise) from footprint of the CHPP, ROM, Product stockpiles & Roadways (haul distance > 1 km but < 2 km). | 231739.506 | m3 | 4.04 | 5.7283 | 1327472.7071 | No change in quantity in 2024 review. Includes scalping carbonaceous material from ROM and two product stockpile areas to depth of 0.5 m.
Earthworks / Structural Works |  | 0 |  |  |  | 10497.6909
1.025 | Replace material from above to expose the concrete reclaim tunnel. 150m - 200 m push length, D11 | 1355.2018 | m3 | 8.04a | 3.2026 | 4340.2218 | No change in quantity in 2024 review. Average excavation depth of 3 m over 450 m2 and will be stockpiled locally and replaced.
1.026 | Excavate material from above to expose the concrete reclaim tunnel. | 1355.2018 | m3 | 9.04 | 4.5436 | 6157.4691 | No change in quantity in 2024 review. Average excavation depth of 3 m over 450 m2 and will be stockpiled locally and replaced.
Domain 1E - Camp (80 man camp) |  | 0 |  |  |  | 194123.2206
Termination of Services and Demolition Works |  | 0 |  |  |  | 194123.2206
1.027 | Disconnect and terminate all services (Water, electricity, gas etc. at point of attachment to site). | 0.9333 | @ | 1.02 | 9490.4819 | 8857.4288 | No change in quantity in 2024 review. A provisional amount used to allow for the removal of services.
1.028 | Demolish and remove infrastructure (accommodation) | 1766.7816 | m2 | 1.08 | 45.0587 | 79608.8244 | No change in quantity in 2024 review. Assume 80 demountable buildings @ 22 m2 area.
1.029 | Remove bitumen (car park and access roads) for dumping in a void on the site. | 12506.0029 | m2 | 1.41 | 8.4485 | 105656.9675 | No change in quantity in 2024 review.
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
1.03 | Remove stabilised material (blue metal, aggregate etc.) from roadways / hardstands / laydown areas and dump in a void on-site (haul distance >1 km but <2 km) | 0 | m3 | 3.08 | 5.7322 | 0 | Not required. Discussed with site.
1.031 | Unsealed roads / vehicle park-up areas – Minor earthworks, final trim and deep rip and seed (pasture grass) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the infrastructure domain.
Domain 1G - Lake horn |  | 0 |  |  |  | 21671.0705
1.032 | Remove surface pipelines. | 100.3853 | m | 1.39 | 16.897 | 1696.2107 | No change in quantity in 2024 review. Estimate assumes some pipes/pumps are located within the dam.
1.033 | Remove pump and pontoon from a small lake or dam including pipes and electrical supply or diesel tank/s. | 0.9333 | @ | 1.40a | 21402.4916 | 19974.8598 | No change in quantity in 2024 review.
Domain 1H - Roads |  | 0 |  |  |  | 1292512.5896
Termination of Services and Demolition Works |  | 0 |  |  |  | 1292512.5896
1.034 | Remove bitumen (car park and access roads) for dumping in a void on the site. | 152987.2243 | m2 | 1.41 | 8.4485 | 1292512.5896 | No change in quantity in 2024 review. Includes all sealed road except for that asP6iated with the Camp, OC1 and surface.
Domain 1I - Other Infrastructure |  | 0 |  |  |  | 8508966.4818
1.035 | Airstrip - Remove bitumen material and dumping in void. | 32986.6154 | m2 | 1.42 | 22.5293 | 743166.4689 | No change in quantity in 2024 review.
1.036 | Removal of powerlines (this includes disconnection, rolling up the wires and removing the poles). It does not include the removal of substations. | 181.7978 | km | 1.03 | 17002.2383 | 3090969.6871 | No change in quantity in 2024 review. Based on the length of all powerlines on site in ERC.
1.037 | Miscellaneous clean-up around site (carbonaceous materials etc) | 0.9333 | @ | SS | 116000 | 108262.336 | Includes 16% escalation for site specific rates in 2014.Provisional sum.
1.038 | Unsealed roads / vehicle park-up areas – Minor earthworks, final trim and deep rip and seed (pasture grass) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now captured within other domains.
1.039 | Provision to dewater sumps and general tidy up of site prior to the commencement of demolition | 0.9333 | @ | SS | 58000 | 54131.168 | Includes 16% escalation for site specific rates in 2014.Provisional sum.
1.04 | Remove stabilised material (blue metal, aggregate etc.) from roadways / hardstands / laydown areas and dump in a void on-site (haul distance >1 km but <2 km) | 0 | m3 | 3.08 | 5.7322 | 0 | Not required. Discussed with site.
1.041 | Fence removal | 4015.4127 | m | 1.48 | 22.5293 | 90464.5732 | No change in quantity in 2024 review. Provisional sum.
1.042 | Demolish and remove small buildings/tanks | 2992.9481 | m2 | 1.09 | 91.3599 | 273435.477 | No change in quantity in 2024 review. Areas calculated for small buildings in Other Lands domain based on rate review. Assume all are single storey buildings.
1.043 | Remove concrete pads and footings (< 0.3 m thickness) from small buildings and dumping in void. | 3292.2429 | m2 | 1.43 | 41.116 | 135363.9717 | No change in quantity in 2024 review. Assume 10% additional footprint for aprons, etc.
1.044 | Demolition/Removal of Dragline. | 0.9333 | @ | SS | 4300000 | 4013172.8 | New Line Added. Rate is based on quote. Quote was $2.7M for the small dragline (CAT 8000 Dragline - BE 1370) and $4.3M for the big one (CAT 8750 Dragline - Marion 8750). Site to confirm size of dragline and most applicable rate. Draglines are 1370s with total out of pocket expense of $2M combined (includes $2.3M for scrap steel , total $4.3M).
Domain 9K - Camp Infrastructure |  | 0 |  |  |  | 18192403.0181
Termination of Services and Demolition Works |  | 0 |  |  |  | 17952708.7931 | Note that in the 2021 costing cells R777-779 were double counted.
1.045 | Disconnect and terminate all services (Water, electricity, gas etc. at point of attachment to site) | 0.9333 | @ | 1.01 | 47518.4566 | 44348.7855 | No change in quantity in 2024 review. For disconnection of all services, at building boundaries, physical cut at the distributions board.
1.046 | Demolish and/or remove substations (Assumes they are in a closed building) | 35.1349 | m2 | 1.06 | 701.8524 | 24659.4865 | No change in quantity in 2024 review.
1.047 | Removal of services (rolling up the wires and removing the poles, removing water/sewage pipes). It does not include the removal of substations. | 33.1272 | km | 1.03 | 17002.2383 | 563235.7795 | No change in quantity in 2024 review. Assumes underground powerlines run along-side roads, therefore equal in length.
1.048 | Demolish and remove small buildings - houses | 506.9459 | @ | SS | 23200 | 11761143.8288 | Includes 16% escalation for site specific rates in 2014.Approximately 505 dwellings.
1.049 | Remove all demountables | 86.3314 | @ | SS | 8120 | 701010.751 | Includes 16% escalation for site specific rates in 2014.86 single person dwellings.
1.05 | Demolish and remove moderate buildings (e.g. school, shopping centre) | 26501.7239 | m2 | 1.1 | 92.2979 | 2446052.5283 | No change in quantity in 2024 review. This includes schools, shopping centres, public building etc (0.75+0.49+0.16+0.17+0.23+0.84= 2.6 ha).
1.051 | Remove concrete pads & footings (<300mm thickness) and dumping in void | 29151.8963 | m2 | 1.43 | 41.116 | 1198610.3626 | No change in quantity in 2024 review. Estimate includes additional 10% for aprons, pathways etc.
1.052 | Remove bitumen (e.g. car park and access roads) | 143652.3936 | m2 | 1.41 | 8.4485 | 1213647.2709 | No change in quantity in 2024 review. The total length of all road at Camp are ~ 20.5 km, assume an average width of 7 m. Demolition expert estimate however economies of scale could reduce this number
Contaminated materials |  | 0 |  |  |  | 239694.225
1.053 | Remove and dispose of asbestos | 5019.2659 | m2 | 4.16 | 45.0587 | 226161.433 | No change in quantity in 2024 review. Remove, contain, transport and dispose of asbestos materials
1.054 | Sale of houses at Middlemount | 23.3324 | @ | SS | 580 | 13532.792 | Includes 16% escalation for site specific rates in 2014.Number of houses confirmed with SCC. Provisional sum for managing sale of houses.
Domain 9L - Camp Water Treatment Plant |  | 0 |  |  |  | 232670.2918
Termination of Services and Demolition Works |  | 0 |  |  |  | 217674.9237
1.055 | Water treatment plant infrastructure | 672.5816 | m2 | 1.1 | 92.2979 | 62077.8483 | No change in quantity in 2024 review. The infrastructure includes small building (220 m2 and 450 m2).
1.056 | Demolish and remove small tank clean (thickener etc 3-9 m diameter) | 1.8666 | @ | 1.28 | 11264.6669 | 21026.5371 | No change in quantity in 2024 review.
1.057 | Demolish and remove small tank clean (thickener etc 15-30 m diameter) | 1.8666 | @ | 1.3 | 72094.2436 | 134570.5383 | No change in quantity in 2024 review.
Contaminated materials |  | 0 |  |  |  | 0
1.058 | Remove stabilised material (blue metal, aggregate etc) from roadways and dump in a void on-site (haul distance >2 km but <5 km) | 0 | m3 | 4.05 | 7.4858 | 0 | Not required. Discussed with site.
Earthworks / Structural Works |  | 0 |  |  |  | 14995.3682
1.059 | Major bulk pushing to achieve grades nominated in the approval/permit - 50 m-100 m push length, D11 | 9679.1523 | ha | 8.02a | 1.5492 | 14995.3682 | Assumes No change in quantity in 2024 review. Assume a average depth of 2.6 m. Assumes evaporation ponds will be pushed in and recontoured.
Domain 9M - Camp Sewage Treatment Plant |  | 0 |  |  |  | 270344.9837
Termination of Services and Demolition Works |  | 0 |  |  |  | 265679.3433
1.06 | Sewage treatment plant infrastructure | 150.578 | m2 | 1.1 | 92.2979 | 13898.0257 | No change in quantity in 2024 review. The infrastructure includes small building (50 m2 and 100 m2).
1.061 | Demolish and remove small tank clean (thickener etc 10-15 m diameter) | 1.8666 | @ | 1.29 | 33794.0007 | 63079.6113 | No change in quantity in 2024 review. Concrete tanks with booms.
1.062 | Demolish and remove small tank clean (thickener etc 15-30 m diameter) | 1.8666 | @ | 1.3 | 72094.2436 | 134570.5383 | No change in quantity in 2024 review. Concrete tanks with booms.
1.063 | Remove contaminated water from maturation pond | 0.9333 | @ | SS | 58000 | 54131.168 | Includes 16% escalation for site specific rates in 2014. Provisional sum.
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 4665.6404
1.064 | Major bulk pushing to achieve grades nominated in the approval/permit - 50 m-100 m push length, D11. CampSewage Treatment Plant | 3011.5595 | m3 | 8.02a | 1.5492 | 4665.6404 | Assumes No change in quantity in 2024 review. Assumes the dam wall will be pushed in and recontoured - 100 x 5 x 3 m. Also includes recontouring around the concrete tanks after removal.
1.065 | Remove stabilised material (blue metal, aggregate etc.) from roadways / hardstands / laydown areas and dump in a void on-site (haul distance >1 km but <2 km) | 0 | m3 | 3.08 | 5.7322 | 0 | Not required. Discussed with site.
Domain 9N - Camp Landfill |  | 0 |  |  |  | 890210.9636
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 402522.16
1.066 | Remove stabilised material (blue metal, aggregate etc.) from roadways / hardstands / laydown areas and dump in a void on-site (haul distance >1 km but <2 km) | 32625.2283 | m3 | 3.08 | 5.7322 | 187014.0089 | No change in quantity in 2024 review. Assume 0.5 m of material is to be removed.
1.067 | Major bulk pushing to achieve grades nominated in the approval/permit - < 50 m push length, D11. CampLandfill. | 194747.5165 | m3 | 8.01a | 1.1066 | 215508.1511 | Assumes No change in quantity in 2024 review. This includes 0.84 ha and 1.09 ha to doze edges and contour, assume ~3 m deep.
Rehabilitation |  | 0 |  |  |  | 487688.8035
1.068 | Cap town landfill - Source local material, cart and spread to cap or backfill. Cap thickness determined by approval/permit (haul distance >5 km) | 48586.4938 | m3 | 6.08 | 10.0375 | 487688.8035 | No change in quantity in 2024 review. Assumes some capping will be required on the active landfill area. Assume 1 m depth across the area of approximately 4.84 ha (specific to this feature).
Total Infrastructure Domain |  | 0 |  |  |  | 8250592.1496
Earthworks / Structural Works |  | 0 |  |  |  | 3098378.6876
1.069 | Minor reshaping and pushing | 424.7303 | ha | 8.08 | 5193.0114 | 2205629.1981 | New line item added in 2024 review. Entire infrastructure domain at LOM.
1.07 | Structural works, banks, waterways | 426.3668 | ha | 8.09 | 2093.853 | 892749.4895 | New line item added in 2024 review. Entire infrastructure domain at LOM.
Rehabilitation |  | 0 |  |  |  | 3945161.1114
1.071 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 426.3668 | ha | 6.1 | 1936.4092 | 825620.6742 | New line item added in 2024 review. Entire infrastructure domain at LOM.
1.072 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 170546.7363 | m3 | 6.03 | 6.8848 | 1174175.4698 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
1.073 | Topsoil amelioration with bio-solids | 256.8058 | ha | 6.23 | 2182.7635 | 560546.3908 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
1.074 | Spoil amelioration (adding gypsum, lime etc.) | 426.3668 | ha | 6.2 | 1170.5459 | 499081.9752 | New line item added in 2024 review. Entire infrastructure domain at LOM.
1.075 | Direct seeding / fertiliser (tree or native grass species) | 13.7528 | ha | 6.15 | 3427.1096 | 47132.3135 | New line item added in 2024 review. Entire infrastructure domain at LOM.
1.076 | Direct seeding / fertiliser (pasture grass species) | 410.9775 | ha | 6.14 | 2040.5115 | 838604.2879 | New line item added in 2024 review. Entire infrastructure domain at LOM.
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 1207052.3506
1.077 | Maintenance of established rehabilitation areas. | 426.3668 | ha | 7.01 | 2110.4388 | 899821.1227 | New line item added in 2024 review. Covers entire infrastructure domain.
1.078 | Existing rehabilitation repair - minor | 128.4029 | ha | 7.06 | 1370.388 | 175961.8085 | Assumes 30% of rehab will require minor repairs.
1.079 | Existing rehabilitation repair - major | 42.801 | ha | 7.08 | 3066.9729 | 131269.4194 | Assumes 10% of rehab will require major repairs.
1.08 | Existing rehabilitation repair - (moderate) | 0 | ha | 7.07 | 1973.4652 | 0 | Zeroed in 2024 as the WM sites all use 10% major/30% minor repairs.
Domain 2 - Tailings and Reject Emplacement Areas |  | 0 |  |  |  | 126403008.3686
Domain 2A - Tailings Storage Facility |  | 0 |  |  |  | 126403008.3686
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
2.001 | Unsealed roads / vehicle park-up areas – Minor earthworks, final trim and deep rip and seed (pasture grass) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated in the infrastructure domain.
Earthworks / Structural Works |  | 0 |  |  |  | 126088188.9127
2.002 | Tailings Storage Facility (Out of Pit) | 1 | @ | SS | 39538755.3398 | 39538755.3398 | Rate provided by site. Volumes and Rates. Hydraulic mining: 5473k m3 at $4.47 Reject Removal: 623k m3 at $12.46 Capping: 133k m3 at $22.73 TOTAL MAT: 6229k m3 at $5.66
2.002 | Tailings Storage Facility (Out of Pit) | 1 | @ | SS | 43824000 | 43824000 | Rate provided by site. Volumes and Rates. Hydraulic mining: 5473k m3 at $4.47 Reject Removal: 623k m3 at $12.46 Capping: 133k m3 at $22.73 TOTAL MAT: 6229k m3 at $5.66
2.003 | Layered tailings capping 3m depth (2 x 1.5m layers) | 31.031 | ha | 8.07b | 384214.6146 | 11922563.7057 | Zeroed as this will be capped at LOM
2.004 | Layered tailings capping 3m depth (2 x 1.5m layers) | 22.477 | ha | 8.07b | 384214.6146 | 8635991.8924 | Zeroed as this will be capped at LOM
2.005 | Layered tailings capping 3m depth (2 x 1.5m layers) | 28.938 | ha | 8.07b | 384214.6146 | 11118402.5173 | Zeroed as this will be capped at LOM
2.006 | Layered tailings capping 3m depth (2 x 1.5m layers) | 28.756 | ha | 8.07b | 384214.6146 | 11048475.4575 | Area updated based on GIS data provided by site. Rate updated as per 2024 WM tailings rates - based on the requirement for 2 x 1.5m layered tailings capping.
2.007 | Fill dams, voids etc. - Source local material, cart and spread to cap or backfill, cap thickness determined by approval / permit ( haul distance >1km but <2km) | 0 | ha | 6.06 | 5.7283 | 0 | Removed in 2024 review. Golder design and cost fir out of pit tailings includes all material. As per the PRCP, the in pit tailings dams will be filled to within 3m of the lowest natural point to allow final capping with 3m cap depth to final landform. 3m cap included in per ha tailings rates above. Note if closure prior to achieving depth of tailings additional material may be required to final landform.,
2.008 | Structural banks, waterways & water management | 0 | ha | 8.09 | 2093.853 | 0 | Not included for this domain as these costs are captured in the overall tailings capping rates above.
2.009 | Minor reshaping and pushing | 0 | ha | 8.08 | 5193.0114 | 0 | Not included for this domain as these costs are captured in the overall tailings capping rates above.
Rehabilitation |  | 0 |  |  |  | 232782.1187
2.01 | Final trim, rock rake & deep rip. | 28.8668 | ha | 6.1 | 1936.4092 | 55897.941 | Area updated in 2024 review. Includes all in pit TSF and out of pit TSF.
2.011 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 11591.2124 | m3 | 6.03 | 6.8848 | 79802.8594 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
2.012 | Topsoil amelioration with bio-solids | 17.3868 | ha | 6.23 | 2182.7635 | 37951.3136 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
2.013 | Direct seeding / fertiliser (pasture grass species) | 28.978 | ha | 6.14 | 2040.5115 | 59130.0047 | Area updated in 2024 review. Includes all in pit TSF and out of pit TSF.
2.014 | Direct seeding / fertiliser (tree or native grass species) | 0 | ha | 6.15 | 3427.1096 | 0 | No pasture rehab at LOM
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 82037.3373
2.015 | Maintenance of established rehabilitation areas. | 28.978 | ha | 7.01 | 2110.4388 | 61156.3607 | Area updated in 2024 review. Includes all in pit TSF and out of pit TSF.
2.016 | Existing rehabilitation repair - minor | 8.7269 | ha | 7.06 | 1370.388 | 11959.2478 | Assumes 30% of rehab will require minor repairs.
2.017 | Existing rehabilitation repair - major | 2.909 | ha | 7.08 | 3066.9729 | 8921.7287 | Assumes 10% of rehab will require major repairs.
2.018 | Existing rehabilitation repair - (moderate) | 0 | ha | 7.07 | 1973.4652 | 0 | Zeroed in 2024 as the WM sites all use 10% major/30% minor repairs.
Domain 3 - Overburden / Waste Emplacement Areas |  | 0 |  |  |  | 26410703.8895
All Overburden emplacement areas |  | 0 |  |  |  | 26410703.8895
Earthworks / Structural Works |  | 0 |  |  |  | 404231.8685
3.001 | Minor reshaping and pushing | 55.4127 | ha | 8.08 | 5193.0114 | 287758.7609 | New domain added in 2024 review. Area as per domain plan pivot table.
3.002 | Structural works, banks, waterways | 55.6262 | ha | 8.09 | 2093.853 | 116473.1076 | New domain added in 2024 review. Area as per domain plan pivot table.
Rehabilitation |  | 0 |  |  |  | 25848993.1986
3.003 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 55.6262 | ha | 6.1 | 1936.4092 | 107715.1057 | New domain added in 2024 review. Area as per domain plan pivot table.
3.004 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 22250.4841 | m3 | 6.03 | 6.8848 | 153189.5201 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
3.005 | Topsoil amelioration with bio-solids | 33.5043 | ha | 6.23 | 2182.7635 | 73132.0274 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
3.006 | Spoil amelioration (adding gypsum, lime etc.) | 278.1311 | ha | 6.2 | 1170.5459 | 325565.1741 | New domain added in 2024 review. Area as per domain plan pivot table. Assumes 5t/ha
3.007 | Direct seeding / fertiliser (tree or native grass species) | 3.2224 | ha | 6.15 | 3427.1096 | 11043.4107 | New domain added in 2024 review. Area as per domain plan pivot table (grazing rehab).
3.008 | Direct seeding / fertiliser (pasture grass species) | 52.1903 | ha | 6.14 | 2040.5115 | 106494.9607 | New domain added in 2024 review. Area as per domain plan pivot table (native ecosystem rehab).
3.009 | Reshaping | 0.86407 | @ | SS | 29016013 | 25071853 | Springbok has two small pits, P6 & BOC, that have had their rehabilitation fail and therefore requires remediation. The current landform shows significant erosion and exhibits steeper grades than are typically acceptable in a reshaped surface. Site specific rate
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 157478.8224
3.01 | Maintenance of established rehabilitation areas. | 55.6262 | ha | 7.01 | 2110.4388 | 117395.7125 | New domain added in 2024 review. Area as per domain plan pivot table.
3.011 | Existing rehabilitation repair - minor | 16.7522 | ha | 7.06 | 1370.388 | 22956.9649 | Assumes 30% of rehab will require minor repairs.
3.012 | Existing rehabilitation repair - major | 5.5841 | ha | 7.08 | 3066.9729 | 17126.145 | Assumes 10% of rehab will require major repairs.
Domain 4 - Active Mining, Pits and Voids |  | 0 |  |  |  | 216537686.3034
Domain 4A |  | 0 |  |  |  | 27642221.6972
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.001 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed in 2024 as these costs are captured in the overall rehabilitation costs for this domain.
Mining and Exploration Works |  | 0 |  |  |  | 0
4.002 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | Zeroed. Site will not use this method. Highwalls will be ripped and pushed to grade instead.
Earthworks / Structural Works |  | 0 |  |  |  | 27642221.6972
4.003 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 11539374.6929 | m3 | 8.03a | 2.3955 | 27642221.6972 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.004 | Load and haul 400 t fleet, flat, <1km | 0 | m3 | 8.2 | 4.5436 | 0 | New Line: Volume provided in Material Volume RFI.
Domain 4B |  | 0 |  |  |  | 14954103.5009
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.005 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed in 2024 as these costs are captured in the overall rehabilitation costs for this domain.
Mining and Exploration Works |  | 0 |  |  |  | 0
4.006 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | Zeroed. Site will not use this method. Highwalls will be ripped and pushed to grade instead.
Earthworks / Structural Works |  | 0 |  |  |  | 14954103.5009
4.007 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 3628501.1548 | m3 | 8.03a | 2.3955 | 8691964.3411 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.008 | Load and haul 400 t fleet, flat, <1km | 1378238.6992 | m3 | 8.2 | 4.5436 | 6262139.1597 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4C | P6 | 0 |  |  |  | 19700709.5673
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.009 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Earthworks / Structural Works |  | 0 |  |  |  | 19700709.5673
4.01 | Major bulk pushing to achieve grades nominated in the approval/permit – 50 m-100 m push length, D11 | 1399625.0908 | m3 | 8.02a | 1.5492 | 2168360.7035 | Zeroed. Volume not provided in materials volume RFI.
4.011 | Load and haul 400 t fleet, flat, <1km | 3858707.2365 | m3 | 8.2 | 4.5436 | 17532348.8638 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4D |  | 0 |  |  |  | 3547615.5913
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.012 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Mining and Exploration Works |  | 0 |  |  |  | 0
4.013 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | Zeroed. Site will not use this method. Highwalls will be ripped and pushed to grade instead.
Earthworks / Structural Works |  | 0 |  |  |  | 3547615.5913
4.014 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 1078858.9789 | m3 | 8.03a | 2.3955 | 2584373.9258 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.015 | Load and haul 400 t fleet, flat, 1-2km | 168154.981 | m3 | 8.21 | 5.7283 | 963241.6655 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4E |  | 0 |  |  |  | 9645268.4993
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.016 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Contaminated materials |  | 0 |  |  |  | 0
4.017 | Remove carbonaceous material (spillage or otherwise) from footprint of the CHPP, ROM, Product stockpiles & Roadway (haul distance >1km but <2km) | 0 | m3 | 4.04 | 5.7283 | 0 | Zeroed in 2024 as no updated data. Note likely error in 2021 sheet. Volume of 1.5m3 used.
Mining and Exploration Works |  | 0 |  |  |  | 0
4.018 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | Zeroed. Site will not use this method. Highwalls will be ripped and pushed to grade instead.
Earthworks / Structural Works |  | 0 |  |  |  | 9645268.4993
4.019 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 2340682.3461 | m3 | 8.03a | 2.3955 | 5607033.4881 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.02 | Load and haul 400 t fleet, flat, 1-2km | 704962.5818 | m3 | 8.21 | 5.7283 | 4038235.0112 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4F |  | 0 |  |  |  | 9669809.5496
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.021 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
4.022 | Remove stabilised material (blue metal, aggregate etc) from roadways / hardstands / laydown areas and dump in a void on-site (haul distance < 1km) | 0 | m3 | 3.07 | 4.6772 | 0 | Not required. As per discussions with site.
Mining and Exploration Works |  | 0 |  |  |  | 0
4.023 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | Zeroed. Site will not use this method. Highwalls will be ripped and pushed to grade instead.
Earthworks / Structural Works |  | 0 |  |  |  | 9669809.5496
4.024 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 3602505.7133 | m3 | 8.03a | 2.3955 | 8629693.0504 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.025 | Load and haul 400 t fleet, flat, 1-2km | 181575.171 | m3 | 8.21 | 5.7283 | 1040116.4992 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4G |  | 0 |  |  |  | 11623080.6606
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.026 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Earthworks / Structural Works |  | 0 |  |  |  | 11623080.6606
4.027 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 2845411.693 | m3 | 8.03a | 2.3955 | 6816097.313 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.028 | Load and haul 400 t fleet, flat, 1-2km | 839164.482 | m3 | 8.21 | 5.7283 | 4806983.3476 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4H |  | 0 |  |  |  | 8271988.2504
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.029 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Earthworks / Structural Works |  | 0 |  |  |  | 8271988.2504
4.03 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 2088317.6727 | m3 | 8.03a | 2.3955 | 5002501.5756 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.031 | Load and haul 400 t fleet, flat, 1-2km | 570760.6816 | m3 | 8.21 | 5.7283 | 3269486.6748 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4I |  | 0 |  |  |  | 4756679.4162
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.032 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0
Earthworks / Structural Works |  | 0 |  |  |  | 4756679.4162
4.033 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 1583588.3258 | m3 | 8.03a | 2.3955 | 3793437.7507 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.034 | Load and haul 400 t fleet, flat, 1-2km | 168154.981 | m3 | 8.21 | 5.7283 | 963241.6655 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4J |  | 0 |  |  |  | 4756679.4162
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.035 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Mining and Exploration Works |  | 0 |  |  |  | 4756679.4162
4.036 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 1583588.3258 | m3 | 8.03a | 2.3955 | 3793437.7507 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.037 | Load and haul 400 t fleet, flat, <1km | 168154.981 | m3 | 8.21 | 5.7283 | 963241.6655 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4K |  | 0 |  |  |  | 9645796.2912
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.038 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Mining and Exploration Works |  | 0 |  |  |  | 0
4.039 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | Zeroed. Site will not use this method. Highwalls will be ripped and pushed to grade instead.
Earthworks / Structural Works |  | 0 |  |  |  | 9645796.2912
4.04 | Major bulk pushing to achieve grades nominated in the approval/permit – 50 m-100 m push length, D11 | 4611964.407 | m3 | 8.02a | 1.5492 | 7145057.9529 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.041 | Load and haul 400 t fleet, flat, 1-2km | 436558.7814 | m3 | 8.21 | 5.7283 | 2500738.3384 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4L |  | 0 |  |  |  | 9783318.0316
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.042 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Mining and Exploration Works |  | 0 |  |  |  | 0
4.043 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | Zeroed. Site will not use this method. Highwalls will be ripped and pushed to grade instead.
Earthworks / Structural Works |  | 0 |  |  |  | 9783318.0316
4.044 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 2719229.3563 | m3 | 8.03a | 2.3955 | 6513831.3568 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.045 | Load and haul 400 t fleet, flat, 1-2km | 570760.6816 | m3 | 8.21 | 5.7283 | 3269486.6748 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4M |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
4.047 | Major bulk pushing to achieve grades nominated in the approval/permit – 50 m-100 m push length, D11 | 0 | m3 | 8.02a | 1.5492 | 0 | Zeroed. Volume not provided in materials volume RFI.
Domain 4N |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
4.048 | Major bulk pushing to achieve grades nominated in the approval/permit – 50 m-100 m push length, D11 | 0 | m3 | 8.02a |  | 0 | No change in quantity in 2024 review.
Domain 4O |  | 0 |  |  |  | 21868577.6543
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.049 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Earthworks / Structural Works |  | 0 |  |  |  | 21868577.6543
4.05 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 7003575.4963 | m3 | 8.03a | 2.3955 | 16776852.4461 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.051 | Load and haul 400 t fleet, flat, <1km | 1120641.4531 | m3 | 8.2 | 4.5436 | 5091725.2082 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4P |  | 0 |  |  |  | 58077221.6243
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.052 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Earthworks / Structural Works |  | 0 |  |  |  | 58077221.6243
4.053 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | 13178042.2269 | m3 | 8.03a | 2.3955 | 31567600.0189 | Volume provided in Material Volume RFI. Push Length 100-150m.
4.054 | Load and haul 400 t fleet, flat, <1km | 5834521.6331 | m3 | 8.2 | 4.5436 | 26509621.6054 | Bulk push as provided in site RFI. Note that data provided was for a 100t fleet, however as there is no WM rate for this, the 400t fleet rate has been used.
Domain 4Q |  | 0 |  |  |  | 0
Mining and Exploration Works |  | 0 |  |  |  | 0
4.055 | Drill and blast faces to make safe the existing high wall areas | 0 | m3 | 5.02 | 2.1254 | 0 | No change in quantity in 2024 review.
4.056 | High wall treatment - (trench and safety berm). | 0 | m | 5.03 | 130.1886 | 0 | No change in quantity in 2024 review.
4.057 | Security fence around steep section of high wall. | 0 | m | 5.04 | 143.2386 | 0 | No change in quantity in 2024 review.
4.058 | Purchase and erect warning signs. | 0 | @ | 5.05 | 242.8891 | 0 | No change in quantity in 2024 review.
4.059 | Active pit area – benches blasted and doze to acceptable grade | 0 | m3 | 5.01 | 2.904 | 0 | No change in quantity in 2024 review.
Earthworks / Structural Works |  | 0 |  |  |  | 0
4.06 | Major bulk pushing to achieve grades nominated in the approval/permit – 50 m-100 m push length, D11 | 0 | m3 | 8.02a | 1.5492 | 0 | No change in quantity in 2024 review.
Domain 4S - Tracks and Other Disturbance |  | 0 |  |  |  | 62459.749
Termination of Services and Demolition Works |  | 0 |  |  |  | 62459.749
4.061 | Demolish and remove demountable structures on concrete stumps - assumes not being re-used | 1386.1872 | m2 | 1.08 | 45.0587 | 62459.749 | No change in quantity in 2024 review. Buildings assumed to be demountables.
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 0
4.062 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these are now consolidated at the bottom of the active mining domain.
Entire Active Mining Domain |  | 0 |  |  |  | 2532156.8039
Earthworks / Structural Works |  | 0 |  |  |  | 952727.6465
4.063 | Minor reshaping and pushing | 130.6013 | ha | 8.08 | 5193.0114 | 678214.0361 | New line item added in 2024 review.
4.064 | Structural works, banks, waterways | 131.1045 | ha | 8.09 | 2093.853 | 274513.6104 | New line item added in 2024 review.
Rehabilitation |  | 0 |  |  |  | 1208269.8314
4.065 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 131.1045 | ha | 6.1 | 1936.4092 | 253872.0154 | New line item added in 2024 review.
4.066 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 52441.8114 | m3 | 6.03 | 6.8848 | 361049.9377 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
4.067 | Topsoil amelioration with bio-solids | 78.9658 | ha | 6.23 | 2182.7635 | 172363.7094 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
4.068 | Spoil amelioration (adding gypsum, lime etc.) | 131.1045 | ha | 6.2 | 1170.5459 | 153463.8737 | New line item added in 2024 review.
4.069 | Direct seeding / fertiliser (tree or native grass species) | 0 | ha | 6.15 | 3427.1096 | 0 | New line item added in 2024 review.
4.07 | Direct seeding / fertiliser (pasture grass species) | 131.1045 | ha | 6.14 | 2040.5115 | 267520.2952 | New line item added in 2024 review.
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 371159.326
4.071 | Maintenance of established rehabilitation areas. | 131.1045 | ha | 7.01 | 2110.4388 | 276688.0834 | New line item added in 2024 review.
4.072 | Existing rehabilitation repair - minor | 39.4829 | ha | 7.06 | 1370.388 | 54106.9045 | Assumes 30% of rehab will require minor repairs.
4.073 | Existing rehabilitation repair - major | 13.161 | ha | 7.08 | 3066.9729 | 40364.3381 | Assumes 10% of rehab will require major repairs.
4.074 | Existing rehabilitation repair - (moderate) | 0 | ha | 7.07 | 1973.4652 | 0 | Zeroed in 2024 as the WM sites all use 10% major/30% minor repairs.
Domain 5 - Water Management |  | 0 |  |  |  | 5720137.523
Water Management |  | 0 |  |  |  | 759326.7314
5.001 | Small clean water dams (i.e. <2ha) to be retained after mine closure – make safe and minor earthworks (Product Stockpiles and ROM) | 3.7332 | @ | 9.03 | 3097.7834 | 11564.5954 | No change in quantity in 2024 review. Assume dams to be retained. Includes rail dams.
5.002 | Small clean water dams (i.e. < 2ha) to be retained after mine closure – make safe and minor earthworks (tracks) | 2.7999 | @ | 9.03 | 3097.7834 | 8673.4466 | No change in quantity in 2024 review. Dams to be retained.
5.003 | Large clean water dams (i.e. >2ha) to be retained after mine closure – make safe and minor earthworks (tracks) | 2.7999 | @ | 9.03a | 11827.9002 | 33116.7959 | No change in quantity in 2024 review. Dams to be retained.
5.004 | Small clean water dams (i.e. < 2ha) to be retained after mine closure – make safe and minor earthworks (A8 Grasstree Pit) | 3.7332 | @ | 9.03 | 3097.7834 | 11564.5954 | No change in quantity in 2024 review. Four x sediment dams
5.005 | Small clean water dams (i.e. < 2ha) to be retained after mine closure – make safe and minor earthworks. A3 Pit | 0.9333 | @ | 9.03 | 3097.7834 | 2891.1489 | No change in quantity in 2024 review. Dams to be retained.
5.006 | Clean water dams to be retained after mine closure – make safe and minor earthworks. Lake Leghorn. | 1.8666 | @ | 9.03a | 11827.9002 | 22077.864 | No change in quantity in 2024 review. Provision to rehabilitate embankments.
5.007 | Drain and remove contaminated sediments from the floor of the dam to enable it to be converted into clean water structure (haul distance <1km). Lake Leghorn. | 101448.3983 | m3 | 9.04 | 4.5436 | 460939.0143 | No change in quantity in 2024 review. Assume 1 m of contaminated sediment to be removed prior to conversion to clean water structure.
5.008 | Drain and remove contaminated sediments from the floor of the dam to enable it to be converted into clean water structure (haul distance >1 km but <2 km). Tailings emplacement area. | 10038.5318 | m3 | 9.05 | 5.7283 | 57503.691 | No change in quantity in 2024 review. Assume 0.5 m of contaminated sediment to be removed prior to conversion to clean water structure.
5.009 | Large clean water dams (i.e. >2ha) to be retained after mine closure – make safe and minor earthworks (tailings emplacement area) | 2.0077 | @ | 9.03a | 11827.9002 | 23746.9505 | No change in quantity in 2024 review. Dams to be retained.
5.01 | Small clean water dams (i.e. < 2ha) to be retained after mine closure – make safe and minor earthworks (P1) | 1.0039 | @ | 9.03 | 3097.7834 | 3109.7197 | No change in quantity in 2024 review. New Turkeys Nest dam. Dam to be retained.
5.011 | Miscellaneous sediment dam and drainage works during mine closure works.(Additional Rehabilitation Works) | 1.0039 | @ | SS | 58000 | 58223.4843 | Includes 16% escalation for site specific rates in 2014. Provisional sum.
5.012 | Small clean water dams (i.e. < 2ha) to be retained after mine closure – make safe and minor earthworks (Additional Rehabilitation Works) | 2.0077 | @ | 9.03 | 3097.7834 | 6219.4394 | No change in quantity in 2024 review. Dam to be retained.
5.013 | Large clean water dams (i.e. >2ha) to be retained after mine closure – make safe and minor earthworks (Additional Rehabilitation Works) | 2.0077 | @ | 9.03a | 11827.9002 | 23746.9505 | No change in quantity in 2024 review. Dam to be retained.
5.014 | Drain and remove contaminated sediment from the floor of the dam to enable it to be converted into clean water structure (haul distance >5 km) (CampWater Treatment Plant) | 2429.3247 | m3 | 9.07 | 10.0375 | 24384.4402 | No change in quantity in 2024 review. Assumes the large dam and 2 small dams at the water treatment plant will remain for the final land-user. Material will be deposited in evaporation pond area.
5.015 | Small clean water dams (i.e. < 2ha) to be retained after mine closure – make safe and minor earthworks (Other infrastructure) | 3.7332 | @ | 9.03 | 3097.7834 | 11564.5954 | No change in quantity in 2024 review. Dam to be retained.
Earthworks / Structural Works |  | 0 |  |  |  | 977064.9391
5.016 | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 50m push length. | 664692.905 | ha | 8.01a | 1.1066 | 735551.0438 | New line item added in 2024. Assumes 2m fill average depth for dams being rehabilitated at closure. Assumes dam walls being pushed in.
5.017 | Minor reshaping and pushing | 33.1071 | ha | 8.08 | 5193.0114 | 171925.4336 | New domain added in 2024 review. Covers entire water management domain being rehabilitated at closure.
5.018 | Structural works, banks, waterways | 33.2346 | ha | 8.09 | 2093.853 | 69588.4617 | New domain added in 2024 review. Covers entire water management domain being rehabilitated at closure.
Creek Diversions |  | 0 |  |  |  | 3582240.5272
5.019 | Long term maintenance of water course diversion – Channel constructed through competent material. Springbok Creek Diversion. | 428.5449 | m | 10.03 | 844.85 | 362056.1841 | No change in quantity in 2024 review. Updated to reflect ERC approach - only 30% of diversion requiring maintenance.
5.02 | Long term maintenance of water course diversion – Channel constructed through competent material. Bull Bull Diversions/Bund | 1153.1261 | m | 10.03 | 844.85 | 974218.6429 | No change in quantity in 2024 review. Updated to reflect ERC approach - only 30% of diversion requiring maintenance.
5.021 | Long term maintenance of Creek diversion – Channel constructed through competent material. Sandy Creek Diversions | 1388.0278 | m | 10.03 | 844.85 | 1172675.3003 | No change in quantity in 2024 review. Updated to reflect ERC approach - only 30% of diversion requiring maintenance.
5.022 | Long term maintenance of Creek diversion – Channel constructed through competent material. Sandy Creek Diversions | 0.9333 | @ | SS | 700000 | 653307.2 | Rate provided by site. (Email from Adam Heap)
5.023 | Long term maintenance of Creek diversion – Channel constructed through competent material. Sandy Creek Diversions | 0.9333 | @ | SS | 300000 | 279988.8 | Rate provided by site. (Email from Adam Heap)
5.024 | Long term maintenance of Creek diversion – Channel constructed through competent material. Sandy Creek Diversions | 0.9333 | @ | SS | 150000 | 139994.4 | Rate provided by site. (Email from Adam Heap)
Rehabilitation |  | 0 |  |  |  | 307417.4347
5.025 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 33.2346 | ha | 6.1 | 1936.4092 | 64355.8729 | New domain added in 2024 review. Covers entire water management domain being rehabilitated at closure.
5.026 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 13293.8581 | m3 | 6.03 | 6.8848 | 91525.1879 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
5.027 | Topsoil amelioration with bio-solids | 20.0176 | ha | 6.23 | 2182.7635 | 43693.7366 | Due to a lack of topsoil available across site, topsoil will be used over 40% of the area, and biosolids over the remaining 60%.
5.028 | Spoil amelioration (adding gypsum, lime etc.) | 33.2346 | ha | 6.2 | 1170.5459 | 38902.6791 | New domain added in 2024 review. Covers entire water management domain being rehabilitated at closure. Assumes 5t/ha.
5.029 | Direct seeding / fertiliser (pasture grass species) | 32.1333 | ha | 6.14 | 2040.5115 | 65568.4496 | New domain added in 2024 review. Covers entire water management domain being rehabilitated at closure.
5.03 | Direct seeding / fertiliser (tree or native grass species) | 0.98378 | ha | 6.15 | 3427.1096 | 3371.5086 | New line item added in 2024 review.
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 94087.8906
5.031 | Maintenance of established rehabilitation areas. | 33.2346 | ha | 7.01 | 2110.4388 | 70139.6848 | New domain added in 2024 review. Covers entire water management domain being rehabilitated at closure.
5.032 | Existing rehabilitation repair - minor | 10.0088 | ha | 7.06 | 1370.388 | 13715.9547 | Assumes 30% of rehab will require minor repairs.
5.033 | Existing rehabilitation repair - major | 3.3363 | ha | 7.08 | 3066.9729 | 10232.2511 | Assumes 10% of rehab will require major repairs.
Domain 6 - Existing Rehabilitation Areas |  | 0 |  |  |  | 23229568.3761
6.001 | Maintenance of established rehabilitation areas. | 8205.3754 | ha | 7.01 | 2110.4388 | 17316942.6213 | Covers all rehabilitation being undertaken (7511.83ha) and completed (662.05 ha) at site, as per domain plan pivot table.
6.002 | Existing rehabilitation repair - minor | 2471.0977 | ha | 7.06 | 1370.388 | 3386362.5381 | Assumes 30% of rehab will require minor repairs.
6.003 | Existing rehabilitation repair - major | 823.6992 | ha | 7.08 | 3066.9729 | 2526263.2166 | Assumes 10% of rehab will require major repairs.
Domain 7 - Offset Areas |  | 0
N/A |  | 0
N/A |  | 0
7.001 |  | 0
Domain 8 - Underground Mining Areas |  | 0 |  |  |  | 18102519.6934
Domain 8A - Vent Fans |  | 0 |  |  |  | 1842289.9857
Termination of Services and Demolition Works |  | 0 |  |  |  | 175781.8501
8.001 | Disconnect and terminate services at remote areas (admin buildings, workshops). | 3.7332 | @ | 1.02 | 9490.4819 | 35429.715 | No change in quantity in 2024 review. A provisional amount used to allow for the removal of services.
8.002 | Demolition and removal of vent raise fans, electrical substation and winch | 2.7999 | @ | 1.27 | 50127.7677 | 140352.1351 | No change in quantity in 2024 review. 3 Return shafts at OCN.
Mining and Exploration Works |  | 0 |  |  |  | 1666508.1356
8.003 | Seal and rehabilitate ventilation shafts | 8.3997 | @ | 5.08 | 198401.7617 | 1666508.1356 | No change in quantity in 2024 review. 9 ventilation shafts
Earthworks / Structural Works |  | 0 |  |  |  | 0
8.004 | Minor reshaping and pushing | 0 | ha | 8.08 | 5193.0114 | 0 | Zeroed as these costs are now captured in other domains.
Rehabilitation |  | 0 |  |  |  | 0
8.005 | Final trim, rock rake & deep rip | 0 | ha | 6.1 | 1936.4092 | 0 | Zeroed as these costs are now captured in other domains.
8.006 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 0 | m3 | 6.03 | 6.8848 | 0 | Zeroed as these costs are now captured in other domains.
8.007 | Direct seeding / fertiliser (pasture grass species) | 0 | ha | 6.14 | 2040.5115 | 0 | Zeroed as these costs are now captured in other domains.
Domain 8B - Springbok North MIA |  | 0 |  |  |  | 1978304.8078
Termination of Services and Demolition Works |  | 0 |  |  |  | 384891.2956
8.008 | Carparks and hardstands - remove bitumen and dispose in onsite void | 45557.352 | m2 | 1.41 | 8.4485 | 384891.2956 | No change in quantity in 2024 review.
Mining and Exploration Works |  | 0 |  |  |  | 1593413.5122
8.009 | Seal drift (width >3m) - backfill the drift for at least 50m against a concrete bulk head with drainage slots. The rate includes some reshaping of batters around the adit entrance. | 3.7332 | @ | 5.06 | 310824.2637 | 1160364.1682 | No change in quantity in 2024 review. Three portal entries and one drift into OCN. Each needs sealing.
8.01 | Remove ancillary infrastructure from around the drift | 3.7332 | @ | SS | 116000 | 433049.344 | Includes 16% escalation for site specific rates in 2014.
Earthworks / Structural Works |  | 0 |  |  |  | 0
8.011 | Minor reshaping and pushing | 0 | ha | 8.08 | 5193.0114 | 0 | Zeroed as these costs are now captured in other domains.
Rehabilitation |  | 0 |  |  |  | 0
8.012 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 0 | ha | 6.1 | 1936.4092 | 0 | Zeroed as these costs are now captured in other domains.
8.013 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 0 | m3 | 6.03 | 6.8848 | 0 | Zeroed as these costs are now captured in other domains.
8.014 | Direct seeding / fertiliser (pasture grass species) | 0 | ha | 6.14 | 2040.5115 | 0 | Zeroed as these costs are now captured in other domains.
Domain 8C- Exploration Areas and mining purpose boreholes |  | 0 |  |  |  | 14110090.0002
Termination of Services and Demolition Works |  | 0 |  |  |  | 2615305.2306
8.015 | Remove gas pipelines | 70107.8782 | m | 1.35 | 29.198 | 2047010.9884 | No change in quantity in 2024 review. Below ground gas pipelines length from ERC 2020.
8.016 | Remove above ground pipe - supported | 42041.0599 | m | 1.38 | 13.5176 | 568294.2423 | No change in quantity in 2024 review. Above ground gas drainage pipelines. Length from ERC 2020.
Mining and Exploration Works |  | 0 |  |  |  | 11494784.7696
8.017 | Bore holes – cap and seal open bore to depth of up to 150m - exploration etc. | 275.3223 | @ | 5.12a | 5378.503 | 1480821.9104 | No change in quantity in 2024 review. Number from ERC 2020. Includes coal quality, ballast holes, geotechnical and structural holes.
8.018 | Geology Bore holes – cap and seal open bore to depth of greater than 150m - < 300m - exploration etc. | 864.2321 | @ | 5.12b | 10371.3653 | 8963266.8005 | No change in quantity in 2024 review. Number from ERC 2020. Includes gas riser, vertical wells, ranging wells, SIS, Goaf, gas permeability, gas compliance.
8.019 | Gas Drainage holes – cap and seal open bore holes - pre-drainage, SIS etc | 70.9305 | @ | 5.12c | 14813.037 | 1050696.0587 | No change in quantity in 2024 review. Number from ERC 2020. Includes Piezometer, water flow, dewatering and raw water.
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 0
8.02 | Land Management (Rehabilitation, weeds, ferals, erosion & seed) | 0 | ha | 7.03 | 450.5867 | 0 | Zeroed as these costs are now captured in other domains.
Domain 8D - Watercourses and Landforms |  | 0 |  |  |  | 53617.6696
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 53617.6696
8.021 | Construction of cut throughs to re-establish surface drainage channels. | 15.866 | @ | 7.05 | 3379.4001 | 53617.6696 | No change in quantity in 2024 review.
Domain 9E - Subsidence Areas |  | 0 |  |  |  | 37020.478
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 37020.478
8.022 | Minor earthworks and maintenance of mine subsidence areas | 20.0771 | ha | 7.04 | 1843.919 | 37020.478 | No change in quantity in 2024 review.
Domain 8E - Other Infrastructure |  | 0 |  |  |  | 81196.752
Minor Reshaping, Final Trim (Roads) |  | 0 |  |  |  | 81196.752
8.023 | General Infrastructure (centre of mine) | 0.9333 | @ | SS | 87000 | 81196.752 | Includes 16% escalation for site specific rates in 2014.Provisional sum
8.024 | Remove stabilised material (blue metal, aggregate etc) from roadways / hardstands / laydown areas and dump in a void on-site (haul distance < 1km) | 0 | m3 | 3.07 | 4.6772 | 0 | Not required. As per disussions with site.
8.025 | Rehabilitation of areas cleared for mining (active) | 0 | ha | 3.03 | 3723.4649 | 0 | Zeroed as these costs are now captured in other domains.
Rehabilitation |  | 0 |  |  |  | 0
8.026 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 0 | ha | 6.1 | 1936.4092 | 0 | Zeroed as these costs are now captured in other domains.
8.027 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 0 | m3 | 6.03 | 6.8848 | 0 | Zeroed as these costs are now captured in other domains.
8.028 | Direct seeding / fertiliser (pasture grass species) | 0 | ha | 6.14 | 2040.5115 | 0 | Zeroed as these costs are now captured in other domains.
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 0
8.029 | Maintenance of established rehabilitation areas. | 0 | ha | 7.01 | 2110.4388 | 0 | Zeroed as these costs are now captured in other domains.
8.03 | Existing rehabilitation repair - (moderate) | 0 | ha | 7.07 | 1973.4652 | 0 | Zeroed as these costs are now captured in other domains.
Domain 9 - Other Lands |  | 0 |  |  |  | 1137592.008
Domain 9D - Clearing Areas |  | 0 |  |  |  | 1137592.008
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 1137592.008
9.001 | Land Management (Rehabilitation, weeds, ferals, erosion & seed) | 2524.6907 | ha | 7.03 | 450.5867 | 1137592.008 | No change in quantity in 2024 review. Assume required for 25% of all other lands undisturbed excluding area in subsidence.
Domain 9F - Airstrip |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
9.002 | Structural banks, waterways & water management | 0 | ha | 8.09 | 2093.853 | 0 | Zeroed as these are now captured within other domains.
Rehabilitation |  | 0 |  |  |  | 0
9.003 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 0 | ha | 6.1 | 1936.4092 | 0 | Zeroed as these are now captured within other domains.
9.004 | Amelioration with agricultural lime | 0 | ha | 6.2 | 1170.5459 | 0 | Zeroed as these are now captured within other domains.
9.005 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 0 | m3 | 6.03 | 6.8848 | 0 | Zeroed as these are now captured within other domains.
9.006 | Direct seeding / fertiliser (pasture grass species) | 0 | ha | 6.14 | 2040.5115 | 0 | Zeroed as these are now captured within other domains.
Domain 9H - Tracks |  | 0 |  |  |  | 0
Rehabilitation |  | 0 |  |  |  | 0
9.007 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 0 | ha | 6.1 | 1936.4092 | 0 | Zeroed as these are now captured within other domains.
9.008 | Direct seeding / fertiliser (tree or native grass species). | 0 | ha | 6.14 | 2040.5115 | 0 | Zeroed as these are now captured within other domains.
Domain 9J - Additional Rehabilitation Works |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
9.009 | Minor reshaping and pushing | 0 | ha | 8.08 | 5193.0114 | 0 | Zeroed as these are now captured within other domains.
Rehabilitation |  | 0 |  |  |  | 0
9.01 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 0 | ha | 6.1 | 1936.4092 | 0 | No change in quantity in 2024 review. Includes areas for buildings, hardstands (excluding Lilyvale substation), soil stockpiles and spoil in this domain.
9.011 | Direct seeding / fertiliser (pasture grass species) | 0 | ha | 6.14 | 2040.5115 | 0 | No change in quantity in 2024 review.
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 0
9.012 | Maintenance of established rehabilitation areas. | 0 | ha | 7.01 | 2110.4388 | 0 | Zeroed as these are now captured within other domains.
9.013 | Existing rehabilitation repair - (moderate) | 0 | ha | 7.07 | 1973.4652 | 0 | Zeroed as these are now captured within other domains.
Domain 9L - Camp Water Treatment Plant |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
9.014 | Minor reshaping and pushing | 0 | ha | 8.08 | 5193.0114 | 0 | Zeroed as these are now captured within other domains.
Domain 9M - CampSewage Treatment Plant |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
9.015 | Minor reshaping and pushing | 0 | ha | 8.08 | 5193.0114 | 0 | Zeroed as these are now captured within other domains.
Domain 9N - CampLandfill |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
9.016 | Minor reshaping and pushing | 0 | ha | 8.08 | 5193.0114 | 0 | Zeroed as these are now captured within other domains.
Domain 9O - Camp Rehabilitation |  | 0 |  |  |  | 0
Earthworks / Structural Works |  | 0 |  |  |  | 0
9.017 | Structural works, banks, waterways | 0 | ha | 8.09 | 2093.853 | 0 | Zeroed as these are now captured within other domains.
Rehabilitation |  | 0 |  |  |  | 0
9.018 | Final trim, rock rake and deep rip (includes minor levelling and landscaping). | 0 | ha | 6.1 | 1936.4092 | 0 | Zeroed as these are now captured within other domains.
9.019 | Source, cart and spread topsoil (@ 0.1 m) haul distance >2km and <5km). | 0 | m3 | 6.03 | 6.8848 | 0 | Zeroed as these are now captured within other domains.
9.02 | Spoil amelioration (adding gypsum, lime etc.) | 0 | ha | 6.2 | 1170.5459 | 0 | Zeroed as these are now captured within other domains.
9.021 | Direct seeding / fertiliser (pasture grass species) | 0 | ha | 6.14 | 2040.5115 | 0 | Zeroed as these are now captured within other domains.
Maintenance of Rehabilitation Areas |  | 0 |  |  |  | 0
9.022 | Maintenance of established rehabilitated areas | 0 | ha | 7.01 | 2110.4388 | 0 | Zeroed as these are now captured within other domains.
9.023 | Existing rehabilitation repair - (moderate) | 0 | ha | 7.07 | 1973.4652 | 0 | Zeroed as these are now captured within other domains.
Whole of Site - Sundry Items and HR/Admin/Stakeholders | [5 empty] | 2130821.2977
Whole of Site A - Sundry Items | [5 empty] | 2130821.2977
Termination of Services and Demolition Works | [5 empty] | 22651.8391
i | Removal and disposal of radiation devices | 1 | each | 1.49 | 22651.8391 | 22651.8391 | No change in quantity in 2024 review.
Contaminated materials | [5 empty] | 340044.765
h | HAZMAT Clean-up - cleaning and decontaminating plant and equipment, chemical storage locations, oil and grease traps, tanks, vessels, and pipe work etc. | 1 | @ | 4.2 | 340044.765 | 340044.765 | No change in quantity in 2024 review.
Heritage Items | [5 empty] | 14573.3471
j | The restoration and care and maintenance of items that have historical significance and are not to be retained after the cessation of mining | 1 | @ | 11.01 | 14573.3471 | 14573.3471 | No change in quantity in 2024 review.
HR, Admin and Sundry Items | [5 empty] | 1190318.0021
a | Stakeholder consultation during closure process | 1 | @ | 12.01 | 50000 | 50000 | No change in quantity in 2024 review.
b | Development of a Planned Project Closure Plan | 1 | @ | 12.02a | 1018873.4431 | 1018873.4431 | Planned project closure plan
n | Monitoring borehole installation | 5 | @ | 12.09 | 24288.9118 | 121444.5589 | No change in quantity in 2024 review. Assume 5 monitoring boreholes unless detailed closure planning shows otherwise.
Third Party Project Management and Contingencies | [5 empty] | 563233.3444
m | Mobilisation & Demobilisation (for large demolition specific equipment only) (Distance to site >500km but <1000km) | 1 | @ | 13.03 | 563233.3444 | 563233.3444 | No change in quantity in 2024 review. Assumes mobilisation from Brisbane.
Total All Domains | [5 empty] | 494115195.0135
Contingencies etc | [5 empty] | 172940318.2547
i | Project management and surveying | 10% | Total | 13.07 | 494115195.0135 | 49411519.5014
ii | Post closure environmental monitoring | 10% | Total | 13.06 | 494115195.0135 | 49411519.5014 | Monitoring contingency increased to 10% as per 2024 WM schedule of rates
iii | Contingency | 15% | Total | 13.05 | 494115195.0135 | 74117279.252 | Updated to 15% in 2024 (Detailed Planning (PFS) (2-5 years until mine closure)
Total + Contingency | [5 empty] | 667055513.2682
Holding Costs | [5 empty] | 232944486.7318
| Holding costs - 5 years during closure execution | 1 | @ |  | 97977763.6857 | 97977763.6857 | Holding costs as provied by WM (refer separate tab)
| Holding costs - 15 years post-closure execution | 1 | @ |  | 134966723.0461 | 134966723.0461 | Holding costs as provied by WM (refer separate tab)
Total + Contingency | [5 empty] | 900000000
|  |  | GRAND TOTAL |  |  | 900000000
Note on A351: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does the UG mine finish up before the open cuts? i.e. would any of these UG costs be completed by LOM?

## BulkPush
Planned Closure Cost Volumes and Push Lengths Required:
Equipment (Dozer) | Planned closure (Active Mining, Pits and Voids): | 2024 Volume (m3) | [14 empty] | Planned Closure Volume (m3) | [5 empty] | Comments
|  | P1 | P2 | P3 | P4 | P5 | P6 | G6 | A3 | A4 | G8 | G5 | G3 | G4 | G7 | G9 | Pit 1 (insert pit name) | Pit 2 | Pit 3 | Pit 4 | Pit 5 | Total
Benches, high wall treatment | Active pit area – benches blasted and doze to acceptable grade | [20 empty] | 0
| Drill & blast faces to make safe | [20 empty] | 0
| High wall treatment – (trench and safety berm) no additional works required to establish | [20 empty] | 0
| High wall treatment – (trench and safety berm) with additional treatment of adjacent loose weathered material | [20 empty] | 0
D10 Major bulk | 50m push length. | [20 empty] | 0
| 50m-100m push length | [20 empty] | 0
| 100m-150m push length | [20 empty] | 0
| 150m - 200 m push length | [20 empty] | 0
| 200m - 300 m push length | [20 empty] | 0
| >300 m push length | [15 empty] | Use load and haul for distances greater than 300m. |  |  |  |  | 0
D11 Major bulk | 50m push length. | [20 empty] | 0
| 50m-100m push length | [20 empty] | 0
| 100m-150m push length | 11495082.1 | 1099857.5 | 12027602.2929 | 6976693.0589 | 3614573.5609 | 1394252.7872 | 2834489.9 | 4594261.9 | 2708791.9 | 2331697.9 | 2080301.9 | 1577509.9 | 1577509.9 | 3588677.9 | 1074717.9 | [5 empty] | 58976020.3999
| 150m - 200 m push length | [20 empty] | 0
| 200m - 300 m push length | [20 empty] | 0
| >300 m push length | [15 empty] | Use load and haul for distances greater than 300m. |  |  |  |  | 0
Equipment (Dozer) | Planned closure (Overburden/Waste Emplacement Areas): | [15 empty] | Planned Closure Volume (m3) | [5 empty] | Comments
[17 empty] | Dump 1 (insert dump name | Dump 2 | Dump 3 | Dump 4 | Dump 5 | Total
D10 Major bulk | 50m push length. | [20 empty] | 0
| 50m-100m push length | [20 empty] | 0
| 100m-150m push length | [20 empty] | 0
| 150m - 200 m push length | [20 empty] | 0
| 200m - 300 m push length | [20 empty] | 0
| >300 m push length | [15 empty] | Use load and haul for distances greater than 300m. |  |  |  |  | 0
D11 Major bulk | 50m push length. | [20 empty] | 0
| 50m-100m push length | [20 empty] | 0
| 100m-150m push length | [20 empty] | 0
| 150m - 200 m push length | [20 empty] | 0
| 200m - 300 m push length | [20 empty] | 0
| >300 m push length | [15 empty] | Use load and haul for distances greater than 300m. |  |  |  |  | 0
Equipment (Dozer) | Planned closure (Tailings Dams): Assuming material that is placed on the approved cap. Ie. Material to get to final landform, after capping. | [15 empty] | Planned Closure Volume (m3) | [5 empty] | Comments
[17 empty] | Tailings Dam 1 (insert TD name | Tailings Dam 2 (insert TD name | Tailings Dam 3 (insert TD name | Tailings Dam 4 (insert TD name | Tailings Dam 5 (insert TD name | Total
D10 Major bulk | 50m push length. | [20 empty] | 0
| 50m-100m push length | [20 empty] | 0
| 100m-150m push length | [20 empty] | 0
| 150m - 200 m push length | [20 empty] | 0
| 200m - 300 m push length | [20 empty] | 0
| >300 m push length | [15 empty] | Use load and haul for distances greater than 300m. |  |  |  |  | 0
D11 Major bulk | 50m push length. | [20 empty] | 0
| 50m-100m push length | [20 empty] | 0
| 100m-150m push length | [20 empty] | 0
| 150m - 200 m push length | [20 empty] | 0
| 200m - 300 m push length | [20 empty] | 0
| >300 m push length | [15 empty] | Use load and haul for distances greater than 300m. |  |  |  |  | 0
Note on I18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reprofiling from 15% to 10% to remedy eroded surface or shape

## Haulage
Imminent Closure - Volumes and Load and Haul Lengths Required: | [26 empty] | Planned Closure - Volumes and Load and Haul Lengths Required:
Imminent closure: | P1 | P2 | P3 | P4 | P5 | P6 | W6 | A3 | A4 | W8 | W5 | W3 | W4 | W7 | W9 | Total (m3) | Comments | 0 | 0 | 0 | 0 | Haul 1 (m3) | Haul 2 (m3) | Haul 3 (m3) | Total (m3) | Comments | Planned closure: | P1 | P2 | P3 | P4 | P5 | P6 | W6 | A3 | A4 | W8 | W5 | W3 | W4 | W7 | W9 | Total (m3) | Comments
800t fleet - Flat | [26 empty] | 100t fleet - Flat
Load and haul 800 t fleet, flat, <1km |  | 568569.8808 | 5812126.4775 | 1116339.9968 | 1372948.4848 | 3843896.0224 | [18 empty] | 12713880.8625 |  | Load and haul 100 t fleet, flat, <1km | 1638064.1311 | 568569.8808 | 5812126.4775 | 1116339.9968 | 1372948.4848 | 3843896.0224 | [9 empty] | 14351944.9936
Load and haul 800 t fleet, flat, 1-2km | [7 empty] | 300000 | 400000 | 500000 | 400000 |  | 100000 |  | 100000 | [9 empty] | 1800000 | See the conceptual option4 | Load and haul 100 t fleet, flat, 1-2km | [6 empty] | 835943.4434 | 434883.0995 | 568569.8808 | 702256.6621 | 568569.8808 | 167509.537 | 167509.537 | 180878.2151 | 167509.537 | 3793629.7927
Load and haul 800 t fleet, flat, 2-5km | [24 empty] | 0 |  | Load and haul 800 t fleet, flat, 2-5km | [15 empty] | 0
Load and haul 800 t fleet, flat, >5km | [24 empty] | 0 |  | Load and haul 800 t fleet, flat, >5km | [15 empty] | 0
600t fleet - Flat | [26 empty] | 600t fleet - Flat
Load and haul 600 t fleet, flat, <1km | [24 empty] | 0 |  | Load and haul 600 t fleet, flat, <1km | [15 empty] | 0
Load and haul 600 t fleet, flat, 1-2km | [24 empty] | 0 |  | Load and haul 600 t fleet, flat, 1-2km | [15 empty] | 0
Load and haul 600 t fleet, flat, 2-5km | [24 empty] | 0 |  | Load and haul 600 t fleet, flat, 2-5km | [15 empty] | 0
Load and haul 600 t fleet, flat, >5km | [24 empty] | 0 |  | Load and haul 600 t fleet, flat, >5km | [15 empty] | 0
400t fleet - Flat | [26 empty] | 400t fleet - Flat
Load and haul 400 t fleet, flat, <1km | 517079.75 | [5 empty] | 487189.06 |  | 542263.77 |  |  | 366634.47 |  | 1539595.47 | [10 empty] | 3452762.52 | Assumed the smaller Truck and Excavator Fleet will be applied. | Load and haul 400 t fleet, flat, <1km | [15 empty] | 0
Load and haul 400 t fleet, flat, 1-2km | [24 empty] | 0 |  | Load and haul 400 t fleet, flat, 1-2km | [15 empty] | 0
Load and haul 400 t fleet, flat, 2-5km | [24 empty] | 0 |  | Load and haul 400 t fleet, flat, 2-5km | [15 empty] | 0
Load and haul 400 t fleet, flat, >5km | [24 empty] | 0 |  | Load and haul 400 t fleet, flat, >5km | [15 empty] | 0
800 t fleet - 50m Elevation | [26 empty] | 800 t fleet - 50m Elevation
Load and haul 800 t fleet, 50m Elevation, <1km | [24 empty] | 0 |  | Load and haul 800 t fleet, 50m Elevation, <1km | [15 empty] | 0
Load and haul 800 t fleet, 50m Elevation, <1-2km | [24 empty] | 0 |  | Load and haul 800 t fleet, 50m Elevation, <1-2km | [15 empty] | 0
Load and haul 800 t fleet, 50m Elevation, 2-5km | [24 empty] | 0 |  | Load and haul 800 t fleet, 50m Elevation, 2-5km | [15 empty] | 0
Load and haul 800 t fleet, 50m Elevation, >5km | [24 empty] | 0 |  | Load and haul 800 t fleet, 50m Elevation, >5km | [15 empty] | 0
600 t fleet - 50m Elevation | [26 empty] | 600 t fleet - 50m Elevation
Load and haul 600 t fleet, 50m Elevation, <1km | [24 empty] | 0 |  | Load and haul 600 t fleet, 50m Elevation, <1km | [15 empty] | 0
Load and haul 600 t fleet, 50m Elevation, <1-2km | [24 empty] | 0 |  | Load and haul 600 t fleet, 50m Elevation, <1-2km | [15 empty] | 0
Load and haul 600 t fleet, 50m Elevation, 2-5km | [24 empty] | 0 |  | Load and haul 600 t fleet, 50m Elevation, 2-5km | [15 empty] | 0
Load and haul 600 t fleet, 50m Elevation, >5km | [24 empty] | 0 |  | Load and haul 600 t fleet, 50m Elevation, >5km | [15 empty] | 0
400 t fleet - 50m Elevation | [26 empty] | 400 t fleet - 50m Elevation
Load and haul 400 t fleet, 50m Elevation, <1km | [24 empty] | 0 |  | Load and haul 400 t fleet, 50m Elevation, <1km | [15 empty] | 0
Load and haul 400 t fleet, 50m Elevation, <1-2km | [24 empty] | 0 |  | Load and haul 400 t fleet, 50m Elevation, <1-2km | [15 empty] | 0
Load and haul 400 t fleet, 50m Elevation, 2-5km | [24 empty] | 0 |  | Load and haul 400 t fleet, 50m Elevation, 2-5km | [15 empty] | 0
Load and haul 400 t fleet, 50m Elevation, >5km | [24 empty] | 0 |  | Load and haul 400 t fleet, 50m Elevation, >5km | [15 empty] | 0
800 t fleet - 100m Elevation | [26 empty] | 800 t fleet - 100m Elevation
Load and haul 800 t fleet, 100m Elevation, <1km | [24 empty] | 0 |  | Load and haul 800 t fleet, 100m Elevation, <1km | [15 empty] | 0
Load and haul 800 t fleet, 100m Elevation, <1-2km | [24 empty] | 0 |  | Load and haul 800 t fleet, 100m Elevation, <1-2km | [15 empty] | 0
Load and haul 800 t fleet, 100m Elevation, 2-5km | [24 empty] | 0 |  | Load and haul 800 t fleet, 100m Elevation, 2-5km | [15 empty] | 0
Load and haul 800 t fleet, 100m Elevation, >5km | [24 empty] | 0 |  | Load and haul 800 t fleet, 100m Elevation, >5km | [15 empty] | 0
600 t fleet - 100m Elevation | [26 empty] | 600 t fleet - 100m Elevation
Load and haul 600 t fleet, 100m Elevation, <1km | [24 empty] | 0 |  | Load and haul 600 t fleet, 100m Elevation, <1km | [15 empty] | 0
Load and haul 600 t fleet, 100m Elevation, <1-2km | [24 empty] | 0 |  | Load and haul 600 t fleet, 100m Elevation, <1-2km | [15 empty] | 0
Load and haul 600 t fleet, 100m Elevation, 2-5km | [24 empty] | 0 |  | Load and haul 600 t fleet, 100m Elevation, 2-5km | [15 empty] | 0
Load and haul 600 t fleet, 100m Elevation, >5km | [24 empty] | 0 |  | Load and haul 600 t fleet, 100m Elevation, >5km | [15 empty] | 0
400 t fleet -100m Elevation | [26 empty] | 400 t fleet -100m Elevation
Load and haul 400 t fleet, 100m Elevation, <1km | [24 empty] | 0 |  | Load and haul 400 t fleet, 100m Elevation, <1km | [15 empty] | 0
Load and haul 400 t fleet, 100m Elevation, <1-2km | [24 empty] | 0 |  | Load and haul 400 t fleet, 100m Elevation, <1-2km | [15 empty] | 0
Load and haul 400 t fleet, 100m Elevation, 2-5km | [24 empty] | 0 |  | Load and haul 400 t fleet, 100m Elevation, 2-5km | [15 empty] | 0
Load and haul 400 t fleet, 100m Elevation, >5km | [24 empty] | 0 |  | Load and haul 400 t fleet, 100m Elevation, >5km | [15 empty] | 0
Fleet Definitions
Fleet Cost ($/bcm) derived on the following basis: Nominal Dig Fleet Combinations: 800t Digger/300t Truck, 600t Digger/220t Truck, 400t Digger/190t Truck Assumed 30% min Pass Match to optimise Full Bucket/Full Truck and define non-haul duration Travel Time assumes 40 km/hr Equivalent Flat Haul Speed, EQF distance calculated from straight line distance and elevation change from WM reference site haul model. Additional operating costs included in unit rates = Dozer @ 1.6hrs per dig hour, Grader/Water Truck @ 0.1 Hrs per Truck Hour, Supervision @ $0.15/bcm

## Holding Costs
Springbok Creek
Holding Costs | 2023 | 2024 YTD | 2024 Fcst | Holding | Execution 5 yr | Post execution (15 yr) | Total holding | yr 1 | yr 2 | yr 3 | yr 4 | yr 5 | yr 6 | yr 7 | yr 8 | yr 9 | yr 10 | yr 11 | yr 12 | yr 13 | yr 14 | yr 15
520110 ¦ Technical Consulting Recharge | 5487150.39 | 3513622.27 | 6023352.4629 | 1600000 | 8000000 | 6352870.9432 | 14352870.9432 | 800000 | 720000 | 648000 | 583200 | 524880 | 472392 | 425152.8 | 382637.52 | 344373.768 | 309936.3912 | 278942.7521 | 251048.4769 | 225943.6292 | 203349.2663 | 183014.3396
540320 ¦ Bank Charges | 157654.42 | 363442.16 | 623043.7029 | 623043.7029 | 3115218.5143 | 4452880.7658 | 7568099.2801 | 560739.3326 | 504665.3993 | 454198.8594 | 408778.9734 | 367901.0761 | 331110.9685 | 297999.8716 | 268199.8845 | 241379.896 | 217241.9064 | 195517.7158 | 175965.9442 | 158369.3498 | 142532.4148 | 128279.1733
540410 ¦ Council Rates | 8224499.08 | 5397383.56 | 9252657.5314 | 9252657.5314 | 46263287.6571 | 66128556.5766 | 112391844.2337 | 8327391.7783 | 7494652.6005 | 6745187.3404 | 6070668.6064 | 5463601.7457 | 4917241.5712 | 4425517.414 | 3982965.6726 | 3584669.1054 | 3226202.1948 | 2903581.9754 | 2613223.7778 | 2351901.4 | 2116711.26 | 1905040.134
540450 ¦ Land Tax | 1857162.62 | 1062435.04 | 1821317.2114 | 1821317.2114 | 9106586.0571 | 13016917.3398 | 22123503.3969 | 1639185.4903 | 1475266.9413 | 1327740.2471 | 1194966.2224 | 1075469.6002 | 967922.6402 | 871130.3761 | 784017.3385 | 705615.6047 | 635054.0442 | 571548.6398 | 514393.7758 | 462954.3982 | 416658.9584 | 374993.0626
Town maintenance | 0 | 0 | 0 | 2000000 | 10000000 | 14293959.6223 | 24293959.6223 | 1800000 | 1620000 | 1458000 | 1312200 | 1180980 | 1062882 | 956593.8 | 860934.42 | 774840.978 | 697356.8802 | 627621.1922 | 564859.073 | 508373.1657 | 457535.8491 | 411782.2642
540460 ¦ Licences / Permits / Registrations | 2574614.15 | 1340811.67 | 2298534.2914 | 2298534.2914 | 11492671.4571 | 16427578.1761 | 27920249.6332 | 2068680.8623 | 1861812.7761 | 1675631.4985 | 1508068.3486 | 1357261.5137 | 1221535.3624 | 1099381.8261 | 989443.6435 | 890499.2792 | 801449.3513 | 721304.4161 | 649173.9745 | 584256.5771 | 525830.9194 | 473247.8274
540470 ¦ Mine Subsidence Levy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540480 ¦ Mines Rescue Levy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540510 ¦ Insurance | 16616587.18 | 8873879.86 | 15212365.4743 | 1500000 | 7500000 | 10720469.7167 | 18220469.7167 | 1350000 | 1215000 | 1093500 | 984150 | 885735 | 797161.5 | 717445.35 | 645700.815 | 581130.7335 | 523017.6602 | 470715.8941 | 423644.3047 | 381279.8742 | 343151.8868 | 308836.6981
540620 ¦ Legal Expenses - Tax Deductible | 213924.91 | 141153.75 | 241977.8571 | 500000 | 2500000 | 3573489.9056 | 6073489.9056 | 450000 | 405000 | 364500 | 328050 | 295245 | 265720.5 | 239148.45 | 215233.605 | 193710.2445 | 174339.2201 | 156905.298 | 141214.7682 | 127093.2914 | 114383.9623 | 102945.566
540760 ¦ Shared Services Fee | 270000.13 | 174953.09 | 299919.5829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35401592.88 | 20867681.4 | 35773168.1143 | 19595552.7371 | 97977763.6857 | 134966723.0461 | 232944486.7318

## 2024 Cost Schedule for Tool
| 1 | 2 | 3 | 5
WM Mine Closure Rates
| # | Activity / Description | Unit | WM 2024 Rate
Activity | 1 | Termination of Services and Demolition Works
Demo | 1.01 | Disconnect and terminate all services (Water, electricity, gas etc. at point of attachment to site) | @ | 47518.4566
Demo | 1.02 | Disconnect and terminate services at remote areas (admin buildings, workshops) | @ | 9490.4819
Demo | 1.03 | Removal of power lines (this includes disconnection, rolling up the wires and removing the poles). It does not include the removal of substations. | km | 17002.2383
Demo | 1.04 | Removal of >66kV power lines (this includes disconnection, rolling up the wires and removing the poles). It does not include the removal of substations. | km | 112646.6689
Demo | 1.05a | Remove small rail, road, water course overpass - smaller structure with minimal civil works | Item | 394263.3411
Demo | 1.05b | Remove medium rail, road, water course overpass - medium structure with minimal civil works | Item | 563233.3444
Demo | 1.05c | Remove large/significant rail, road, water course overpass - large structure with significant water management and civil works | Item | 2186002.0609
Demo | 1.06 | Demolish and/or remove substations (Assumes they are in a closed building) | m2 | 701.8524
Demo | 1.07 | Demolish and remove switchyard/gas flare plant | m2 | 73.5484
Demo | 1.08 | Demolish and remove demountable structures on concrete stumps - assumes not being re-used | m2 | 45.0587
Demo | 1.08a | Demolish and remove demountable structures on concrete stumps - assumes not being re-used - each | Unit | 2467.2437
Demo | 1.09 | Demolish and remove small buildings/tanks (admin buildings, single story accommodation etc.) | m2 | 91.3599
Demo | 1.1 | Demolish and remove light industrial buildings | m2/floor | 92.2979
Demo | 1.11 | Demolish and remove industrial buildings (workshops tyre change and servicing area etc. - not CHPP) | m2/floor | 175.7288
Demo | 1.12 | Demolish and remove CHPP (include the area of each floor of the structure) | m2/floor | 247.8264
Demo | 1.13 | Demolish and remove crushers, hoppers, sizing stations, rotary breakers, etc. (include the area of each floor of the structure). | m2/floor | 253.455
Demo | 1.14 | Demolish and remove stacker or reclaimer (radial or luffing etc.) | @ | 1099045.7507
Demo | 1.15 | Demolish and remove bucket wheel stacker/reclaimer | @ | 2252933.3776
Demo | 1.16 | Remove stacker/reclaimer rails and ballast etc. | m | 84.485
Demo | 1.17 | Collapse, Cut and Remove 5000T coal silo | @ | 123726.6521
Demo | 1.18 | Collapse, Cut and Remove 2000/3000 T coal silo | @ | 104120.7312
Demo | 1.19 | Collapse, Cut and Remove 1250 T coal silo | @ | 77940.9378
Demo | 1.2 | Collapse, Cut and Remove rail loading bins | @ | 76881.3515
Demo | 1.20a | Demolish and Remove large concrete rail loading bin - and disposal on-site/locally | allow | 518174.6769
Demo | 1.21 | Demolish and remove on-ground conveyors, transfer stations & gantries (scrap only – does not include dismantling for reuse at another site) | m | 225.6427
Demo | 1.22 | Demolish and remove elevated conveyors, transfer stations & gantries (scrap only – does not include dismantling for reuse at another site) | m | 463.0575
Demo | 1.23 | Demolish and remove overhead conveyors, transfer stations & gantries (scrap only – does not include dismantling for reuse at another site) | m | 957.4967
Demo | 1.24 | Demolish reclaim tunnel, cut reo and expose reclaim conveyor, then collapse into the reclaim tunnel void (Does not include excavation to expose reclaim tunnel, removal of conveyor or backfilling void) | m2 | 107.0143
Demo | 1.25 | Remove and demolish conveyor from reclaim tunnel (Does not include excavation and demolition of reclaim tunnel roof) | m | 168.97
Demo | 1.26 | Demolition of reclaim tunnel concrete (Assumes complete removal and dumping in mine pit void) | m | 1070.1434
Demo | 1.27 | Demolition and removal of vent raise fans, electrical substation and winch | @ | 50127.7677
Demo | 1.28 | Demolish and remove small tank clean (Thickener etc. 3 - 9 m diameter) | @ | 11264.6669
Demo | 1.29 | Demolish and remove medium tank clean (Thickener etc. 10 - 15 m diameter) | @ | 33794.0007
Demo | 1.3 | Demolish and remove large tank clean (Thickener etc. 15 - 30 m diameter) | @ | 72094.2436
Demo | 1.31 | Demolish and remove extra large tank clean (Thickener etc. >30 m diameter) | @ | 104198.1687
Demo | 1.32 | Demolish and remove tank clean (Thickener etc.) >50 m diameter | @ | 197131.6705
Demo | 1.33 | Removal of UG tank <5000L - including pipes, bunds etc. | @ | 18023.0915
Demo | 1.34 | Removal of UG tank 5000L - 15000L - including pipes, bunds etc. | @ | 33794.0007
Demo | 1.35 | Remove small underground pipe (unless approved to be terminated and left in situ) | m | 29.198
Demo | 1.36 | Remove medium underground pipe (unless approved to be terminated and left in situ) | m | 67.588
Demo | 1.37 | Remove large underground pipe (unless approved to be terminated and left in situ) | m | 185.867
Demo | 1.38 | Remove above ground pipe - supported | m | 13.5176
Demo | 1.39 | Remove surface pipelines - unsupported | m | 16.897
Demo | 1.4 | Remove pump and pontoon from a large lake or dam including pipes and electrical supply or diesel tank/s | @ | 0
Demo | 1.40a | Remove pump and pontoon from a small lake or dam including pipes and electrical supply or diesel tank/s | @ | 21402.4916
Demo | 1.41 | Remove bitumen (car park and access roads) for dumping in a void on the site | m2 | 8.4485
Demo | 1.42 | Remove bitumen (airstrip) for dumping in a void on-site | m2 | 22.5293
Demo | 1.43 | Remove concrete pads & footings (<300mm thickness) and dumping in void | m2 | 41.116
Demo | 1.44 | Remove concrete pads & footings (>300mm thickness)and dumping in void | m2 | 84.485
Demo | 1.45 | Crush concrete to make road aggregate - 75mm | tonne | 11.2647
Demo | 1.46 | Crush concrete to make road aggregate - 50mm | tonne | 15.4889
Demo | 1.47 | Crush concrete to make road aggregate - 30mm | tonne | 17.1786
Demo | 1.48 | Remove fence (cyclone/wire fence) | m | 22.5293
Demo | 1.49 | Removal and disposal of radiation devices | each | 22651.8391
Demo | 1.5 | Removal of small plastic tanks | each | 1126.4667
Demo | 1.51 | Demolish and remove communication towers | each | 5632.3334
Demo | 1.52 | Removal of UG services (power within main gate areas, etc.) | allow | 56323.3344
Demo | 1.53 | Waste disposal to Council landfill - fees (general waste) | tonne | 249.211
Demo | 1.54 | Waste disposal to Council landfill - fees (industrial demolition / concrete / scrap metal) | tonne | 273.3958
Demo | 2 | Rail Infrastructure
Demo | 2.01 | Remove rail loop and spur, ballast etc. | m | 63.0821
Demo | 2.02 | Remove train loading facilities | m2 | 208.3963
Demo | 2.03 | Reshape rail spur and load out areas - does not include topsoil and revegetation | ha | 3221.6947
Earthworks | 3 | Minor Reshaping, Final Trim (Roads)
Earthworks | 3.01 | Unsealed roads / vehicle park-up areas – minor works including deep rip and trim | ha | 1035.1075
Earthworks | 3.02 | Unsealed roads / access tracks / vehicle park-up areas with windrows and/or small earthen bunds – minor earthworks and deep rip and trim | ha | 1697.2017
Earthworks | 3.03 | Unsealed roads / vehicle park-up areas – Minor earthworks, final trim and deep rip and seed (pasture grass) | ha | 3723.4649
Earthworks | 3.04 | Unsealed roads / vehicle park-up areas – Minor earthworks, final trim and deep rip, ameliorate and seed (native tree/shrub/grass) | ha | 5185.7374
Earthworks | 3.05 | Unsealed roads / haul roads / vehicle park-up areas with windrows and/or small earthen bunds – Minor earthworks, final trim and deep rip, ameliorate and seed (pasture grass) | ha | 5232.5598
Earthworks | 3.06 | Unsealed roads / haul roads / vehicle park-up areas with windrows and/or small earthen bunds – Minor earthworks, final trim and deep rip, ameliorate and seed (native tree/shrub/grass) | ha | 7461.6042
Load and haul | 3.07 | Remove stabilised material (blue metal, aggregate etc.) from roadways and dump in a void on-site (haul distance < 1km) | m3 | 4.6772
Load and haul | 3.08 | Remove stabilised material (blue metal, aggregate etc.) from roadways and dump in a void on-site (haul distance >1 km but <2 km) | m3 | 5.7322
Load and haul | 3.09 | Remove stabilised material (blue metal, aggregate etc.) from roadways and dump in a void on-site (haul distance >2 km but <5 km) | m3 | 8.1106
Load and haul | 3.1 | Remove stabilised material (blue metal, aggregate etc.) from roadways and dump in a void on-site (haul distance >5 km) | m3 | 10.6451
Contam | 4 | Contaminated Materials
Contam | 4.01 | Undertake Phase 1 contamination assessment - assumes potential contamination is localised. If there are multiple work areas on site, additional studies should be included. | Item | 14573.3471
Contam | 4.01a | Undertake an intrusive (or Phase 2) site investigation. This accounts for current and historical locations where areas of disturbance are clustered (i.e. located in close proximity and easily accessible such as same MIA, STP and nearby camp, or other areas within ~ 5km). If there are multiple cluster areas on site, multiple intrusive investigations should be included. | Cluster | 103567.9199
Contam | 4.01b | Develop a Remediation Action Plan on sites with large footprints based on outcomes of intrusive investigation including strategies to address contamination exceedances | allow | 34004.4765
Contam | 4.02 | Removal and disposal of oil contaminated water from bunded areas and sumps | L | 0.34004
Load and haul | 4.03 | Remove carbonaceous material (spillage or otherwise) from footprint of the CHPP, ROM, Product stockpiles & Roadways (haul distance < 1km) | m3 | 4.5436
Load and haul | 4.04 | Remove carbonaceous material (spillage or otherwise) from footprint of the CHPP, ROM, Product stockpiles & Roadway (haul distance >1km but <2km) | m3 | 5.7283
Load and haul | 4.05 | Remove carbonaceous material (spillage or otherwise) from footprint of the CHPP, ROM, Product stockpiles & Roadway (haul distance >2km but <5km) | m3 | 7.4858
Load and haul | 4.06 | Remove carbonaceous material (spillage or otherwise) from footprint of the CHPP, ROM, Product stockpiles & Roadway (haul distance >5km) | m3 | 10.0375
Load and haul | 4.07 | Load, cart and disposal of Restricted classified contaminated material off site to a licensed landfill. Add $50/m3 for cartage from regional areas | m3 | 743.468
Load and haul | 4.07a | Load, cart and dispose of Hazardous classified contaminated material off site to a licensed landfill. Assumes cartage to a licensed landfill. | m3 | 901.1734
Load and haul | 4.08 | Load, cart and disposal of Low Level contaminated material off site to a licensed landfill. Add $50/m3 for cartage to regional landfill | m3 | 247.8227
Contam | 4.09 | Onsite remediation of hydrocarbon contaminated soils (<50m3) - manual land farming | m3 | 112.6467
Contam | 4.09a | Construct and set up bioremediation pad | allow | 38862.2589
Contam | 4.1 | Onsite remediation of hydrocarbon contaminated soils (>50m3 but <100m3) - manual land farming | m3 | 116.2288
Contam | 4.11 | Onsite remediation of hydrocarbon contaminated soils (>100m3 but <500m3) - manual land farming | m3 | 89.1486
Contam | 4.12 | Onsite remediation of hydrocarbon contaminated soils (>500m3) - manual land farming | m3 | 84.485
Contam | 4.13 | Mobilisation of mobile treatment unit for hydrocarbon contaminated soil treatment | Item | 168970.0033
Contam | 4.14 | Onsite remediation of hydrocarbon contaminated soils - using a mobile treatment unit | m3 | 185.867
Contam | 4.15 | Remove and dispose of asbestos (Single storey structure) | m2 | 137.961
Contam | 4.16 | Remove and dispose of asbestos (Double storey structure) | m2 | 45.0587
Contam | 4.17a | Waste disposal to Council landfill - fees (asbestos) | tonne | 317.3294
Contam | 4.19 | Removal and disposal of plastic liner (i.e. dam, leach pad etc.) | m2 | 1.1265
Contam | 4.19a | Removal and remediation of hydrocarbons | allow | 291466.9415
Contam | 4.2 | Medium HAZMAT Clean-up - cleaning and decontaminating plant and equipment, chemical storage locations, oil and grease traps, tanks, vessels, and pipe work etc. | @ | 340044.765
Contam | 4.20a | Large HAZMAT Clean-up - cleaning and decontaminating plant and equipment, chemical storage locations, oil and grease traps, tanks, vessels, and pipe work etc | @ | 732203.3477
Contam | 4.21 | Collection, destruction and certification of washery control panels containing Sulfur Hexafluoride ( SF6 ) | @ | 1165.8678
Contam | 4.22 | Disposal of Firebox AFFF 6% fire fighting foam at certified disposal site | kg | 6.8009
Mining/sealing | 5 | Mining and Exploration Works
Mining/sealing | 5.01 | Active pit area – benches blasted and doze to acceptable grade | m3 | 2.904
Mining/sealing | 5.02 | Drill & blast faces to make safe | m3 | 2.1254
Mining/sealing | 5.03 | High wall treatment – (trench and safety berm) no additional works required to establish | m | 130.1886
Mining/sealing | 5.03a | High wall treatment – (trench and safety berm) with additional treatment of adjacent loose weathered material | m | 676.9805
Mining/sealing | 5.04 | Security fence around steep section of high wall | m | 143.2386
Mining/sealing | 5.05 | Purchase and erect warning signs | @ | 242.8891
Mining/sealing | 5.06 | Seal portals / adits (width >3m) – backfill the adit for at least 50 m against a concrete bulk head with drainage slots. The rate includes some reshaping of batters around the adit entrance. If concrete bulk head not required, reduce rate by 25% | @ | 310824.2637
Mining/sealing | 5.07 | Seal small adits (width <3m) – install concrete plug / plugs metres back from adit and backfill with appropriate material. The rate includes some reshaping of the batter around the entrance of the adit | @ | 72832.5053
Mining/sealing | 5.08 | Seal and rehabilitate ventilation fans shafts - allows for works in a remote location | @ | 198401.7617
Mining/sealing | 5.08a | Shaft filling - includes filling of shafts with stockpiled materials | m3 | 103.6327
Mining/sealing | 5.08b | Demolish ventilation fans |  | 46972.2682
Mining/sealing | 5.09 | Maintenance and monitoring of sealed adits/portals and shafts (5 years) | @ | 28161.6672
Mining/sealing | 5.11 | Bore holes – backfill open bore holes with cuttings | @ | 47.8748
Mining/sealing | 5.12a | Bore holes – cap and seal open bore to depth of up to 150m - exploration etc. | @ | 5378.503
Mining/sealing | 5.12b | Bore holes – cap and seal open bore to depth of greater than 150m - < 300m - exploration etc. | @ | 10371.3653
Mining/sealing | 5.12c | Bore holes – cap and seal open bore to depth of greater than 300m - exploration etc. | @ | 14813.037
Mining/sealing | 5.17 | Bore holes – cap and seal service boreholes for UG operations | @ | 43234.263
Rehab | 6 | Rehabilitation
Load and haul | 6.01 | Source, cart and spread topsoil haul distance <1km | m3 | 4.054
Load and haul | 6.02 | Source, cart and spread topsoil haul distance >1km but <2km) | m3 | 4.8265
Load and haul | 6.03 | Source, cart and spread topsoil haul distance >2km but <5km) | m3 | 6.8848
Load and haul | 6.04 | Source, cart and spread topsoil haul distance >5km | m3 | 8.5551
Load and haul | 6.05 | Fill dams, voids etc. - Source local material, cart and spread to cap or backfill, cap thickness determined by approval / permit (haul distance <1 km) | m3 | 4.5436
Load and haul | 6.06 | Fill dams, voids etc. - Source local material, cart and spread to cap or backfill, cap thickness determined by approval / permit ( haul distance >1km but <2km) | m3 | 5.7283
Load and haul | 6.07 | Fill dams, voids etc. - Source local material, cart and spread to cap or backfill, cap thickness determined by approval / permit ( haul distance >2km but <5km) | m3 | 7.4858
Load and haul | 6.08 | Fill dams, voids etc. - Source local material, cart and spread to cap or backfill, cap thickness determined by approval / permit ( haul distance >5km) | m3 | 10.0375
Bulk push | 6.08a | Material movement by dragline | m3 | 0.97156
Rehab | 6.09 | Shot-creting cuttings and steep slopes | m2 | 160.3068
Rehab | 6.1 | Final trim, rock rake & deep rip (includes minor levelling and landscaping) | ha | 1936.4092
Rehab | 6.11 | Deep rip hard stand / lay down areas | ha | 1010.7831
Rehab | 6.12 | Planting mature trees (>15cm) | @ | 18.2167
Rehab | 6.13 | Planting tube stock (<15cm) | @ | 5.6607
Rehab | 6.14 | Direct seeding / fertiliser (pasture grass species) | ha | 2040.5115
Rehab | 6.15 | Direct seeding / fertiliser (tree or native grass species) | ha | 3427.1096
Rehab | 6.16 | Hydro-seeding with straw mulching and bitumen tack | m2 | 2.084
Rehab | 6.16a | Hydro-seeding with straw mulching and bitumen tack with pasture seed | m2 | 0.92298
Rehab | 6.16b | Hydromulch - base grade or standard for flat areas that can be irrigated by water cart | m2 | 0.8744
Rehab | 6.16c | Hydromulch - bonded fibre matrix grade for steep areas to stabilise up to 12 months | m2 | 1.4573
Rehab | 6.17 | Single application of fertiliser (pasture) | ha | 614.292
Rehab | 6.18 | Single application of fertiliser (trees) | ha | 219.661
Rehab | 6.19 | Amelioration with agricultural lime | t | 335.187
Rehab | 6.2 | Spoil amelioration (adding lime etc.) | ha | 1170.5459
Rehab | 6.21 | Amelioration with gypsum | t | 221.3818
Rehab | 6.22 | Amelioration with recycled gypsum | t | 650.9428
Rehab | 6.23 | Topsoil amelioration with bio-solids | ha | 2182.7635
Rehab | 6.24 | Construct no-climb stock fence around rehabilitated areas | m | 20.0141
Rehab | 6.25 | Construct standard stock fence around rehabilitated areas | m | 21.086
Rehab | 6.26 | Supply from external sources virgin excavated natural material (VENM) for filing voids and/or capping etc. | m3 | 91.0185
Rehab | 6.27 | Supply from external sources a combination of virgin excavated natural material (VENM) and spoil from large excavation for filing voids and/or capping etc. | m3 | 81.0493
Rehab | 6.28 | Clearing and grubbing of trees and vegetation | ha | 4775.2001
Rehab | 6.29 | Topsoil stripping | m3 | 4.0031
Rehab | 7 | Maintenance of Rehabilitated Areas
Rehab | 7.01 | Maintenance of areas that have been shaped and seeded and rehabilitation has been classified as "successful" | ha | 2110.4388
Rehab | 7.02 | Pest management on buffer lands, non-disturbed, and rehabilitated areas | ha | 168.97
Rehab | 7.03 | Land management of undisturbed areas (rehabilitation, weeds, feral animals, erosion and sediment control works) | ha | 450.5867
Rehab | 7.04 | Minor earthworks and maintenance of mine subsidence areas | ha | 1843.919
Rehab | 7.04a | Crack filling to repair subsidence impacts | m | 1633.3767
Rehab | 7.05 | Create cut-through to re-establish natural water courses/drainage channels following subsidence | @ | 3379.4001
Rehab | 7.06 | Existing rehabilitation repair - minor | ha | 1370.388
Rehab | 7.07 | Existing rehabilitation repair - moderate | ha | 1973.4652
Rehab | 7.08 | Existing rehabilitation repair - major | ha | 3066.9729
Rehab | 7.09 | Existing rehabilitation repair - total failure of landform | ha | 49418.752
Earthworks | 8 | Earthworks / Structural Works
Bulk Push D10
Bulk push | 8.01 | D10 - Major bulk pushing to achieve grades nominated in the approval/permit – 50m push length. | m3 | 1.8096
Bulk push | 8.02 | D10 -Major bulk pushing to achieve grades nominated in the approval/permit – 50m-100m push length | m3 | 2.5908
Bulk push | 8.03 | D10 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | m3 | 4.114
Bulk push | 8.04 | D10 - Major bulk pushing to achieve grades nominated in the approval/permit -150m - 200 m push length | m3 | 5.5591
Bulk push | 8.05 | D10 -Major bulk pushing to achieve grades nominated in the approval/permit -200m - 400 m push length | m3 | 9.699
Bulk push | 8.06 | D10 - Major bulk pushing to achieve grades nominated in the approval/permit >400 m push length | m3 | 11.704
Bulk Push D11
Bulk push | 8.01a | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 50m push length. | m3 | 1.1066
Bulk push | 8.02a | D11 -Major bulk pushing to achieve grades nominated in the approval/permit – 50m-100m push length | m3 | 1.5492
Bulk push | 8.03a | D11 - Major bulk pushing to achieve grades nominated in the approval/permit – 100m-150m push length | m3 | 2.3955
Bulk push | 8.04a | D11 - Major bulk pushing to achieve grades nominated in the approval/permit -150m - 200 m push length | m3 | 3.2026
Bulk push | 8.05a | D11 -Major bulk pushing to achieve grades nominated in the approval/permit -200m - 400 m push length | m3 | 5.4289
Bulk push | 8.06a | D11 - Major bulk pushing to achieve grades nominated in the approval/permit >400 m push length | m3 | 6.4964
Tailings Capping - TBC
Tailings | 8.07 | Ideal Tailings Capping (2m) Current Dam consolidation (ie. consolidated, partial, no consolidation) – consolidated - supports mining equipment Geochemical Issues issues – No - Assumes no seepage issues require significant aftercare or maintenance. Little chemical reactivity (no to low risk Potential Acid Forming (PAF) / Neutral Mine Drainage (NMD) / Saline Mine Drainage (SMD) and/or low to moderate propensity for spontaneous combustion). Geochemistry adequately managed with cap. Geotextile spread required? – No Return haul distance – 1-2km (if longer haul is required see long haulage rates). Fleet used for capping - Assumes capping material hauled to tailings area and onto cap mining fleet and D11 shaping. Capping Depth - Spoil depth approximately 2 m placed with larger earthmoving fleet. Assumes compaction achieved via traffic. Design costs – Allows 7% design costs, 12% construction supervision and geotechnical investigation, 30% for contractor indirects | ha | 168908.2764
Tailings | 8.07a | Ideal Tailings Capping (3m) Current Dam consolidation (ie. consolidated, partial, no consolidation) – consolidated - supports mining equipment Geochemical Issues issues – No - Assumes no seepage issues require significant aftercare or maintenance. Little chemical reactivity (no to low risk Potential Acid Forming (PAF) / Neutral Mine Drainage (NMD) / Saline Mine Drainage (SMD) and/or low to moderate propensity for spontaneous combustion). Geochemistry adequately managed with cap. Geotextile spread required? – No Return haul distance – 1-2km (if longer haul is required see long haulage rates). Fleet used for capping - Assumes capping material hauled to tailings area and onto cap mining fleet and D11 shaping. Capping Depth - Spoil depth approximately 3 m placed with larger earthmoving fleet. Assumes compaction achieved via traffic. Design costs – Allows 7% design costs, 12% construction supervision and geotechnical investigation, 30% for contractor indirects | ha | 248225.1752
Tailings | 8.07b | Layered Tailings Capping Current Dam consolidation (ie. consolidated, partial, no consolidation) – tailings rested for between 3 and 5 years, wastes not significantly hydrophilic or holding water, well managed. First layer to be spread by smaller gear Geochemical Issues issues – Assumes no seepage issues require significant aftercare or maintenance. Little chemical reactivity (no to low risk Potential Acid Forming (PAF) / Neutral Mine Drainage (NMD) / Saline Mine Drainage (SMD) and/or low to moderate propensity for spontaneous combustion). Geochemistry adequately managed with cap. Geotextile spread required? – No Return haul distance – 1-2km (if longer haul is required see long haulage rates). Fleet used for capping - Assumes capping hauled to tailings area with larger fleet and onto cap with 30t ADT and D6 push for first layer used. Second layer with larger civil fleet. Capping Depth - Spoil depth average cap thickness of 2 m thickness spread in 2 x 1m layers. Assumes compaction achieved via traffic. Design costs – Allows 5% design costs, 10% construction supervision and geotechnical investigation, 30% for contractor indirects | ha | 384214.6146
Tailings | 8.07c | Multi layer Adverse Tailings Capping Current Dam consolidation (ie. consolidated, partial, no consolidation) – low shear strength that prohibits economically efficient construction methods. Tailings rested for between 3 and 5 years, wastes not significantly hydrophilic or holding water, Geochemical Issues issues – moderate chemical reactivity (medium to high risk. Potential Acid Forming (PAF) / Neutral Mine Drainage (NMD) / Saline Mine Drainage (SMD) and/or moderate to high propensity for spontaneous combustion). Geotextile spread required? – Yes. Return haul distance – 1-2km (if longer haul is required see long haulage rates). Fleet used for capping - Assumes capping hauled to tailings area with larger fleet. First layer with marooka and Dozer D6 LGP. 30t ADT and D6 push for second layer used. Third layer with larger civil fleet. Capping Depth - Spoil depth average cap thickness ranging from 2 m thickness above cap for final landform with larger earthmoving fleet. Assumes compaction achieved via traffic. Design costs – Allows 7% design costs, 12% construction supervision and geotechnical investigation, 30% for contractor indirects Capping Depth - Spoil depth 2m thickness above cap spread in layers for final landform with larger earthmoving fleet. Assumes compaction achieved via traffic. | ha | 598819.5667
Tailings | 8.07d | Difficult Tailings Capping Difficult conditons or immediate capping required) - Could be unconsolidated, geochemical issues, Current Dam consolidation (ie. consolidated, partial, no consolidation) – weak or soft surfaced tailings facility with poor physical properties. This option can be driven by time constraints. Geochemical Issues (potentially)– high risk Potential Acid Forming (PAF) / Neutral Mine Drainage (NMD) / Saline Mine Drainage (SMD) and/or moderate to high propensity for spontaneous combustion). Geotextile spread required? – Artificial strengthening is likely required Return haul distance – 1-2km (if longer haul is required see long haulage rates Fleet used for capping - Assumes capping hauled to tailings area with larger fleet. First layer with marooka and Dozer D6 LGP/tracked loader. 30t ADT and D6 push for second layer used. Third layer with larger civil fleet. Capping Depth - Spoil depth greater than 4m thickness above cap for final landform with larger earthmoving fleet. Assumes compaction achieved via traffic. Design costs – Allows 10% design costs, 20% construction supervision and geotechnical investigation, 30% for contractor indirects | ha | 720285.3833
Civils
Earthworks | 8.08 | Minor reshaping and pushing | ha | 5193.0114
Earthworks | 8.09 | Structural works, banks, waterways - contour banks, drainage channels and other soil conservation measures | ha | 2093.853
Earthworks | 8.1 | Construction of engineered landform stabilisation works including rock lined drop structures etc. | m2 | 40.9584
Earthworks | 8.10a | Import of rock material for constuction of drains etc | m3 | 77.7245
Earthworks | 8.11 | Construction of water course entry points | @ | 97155.6472
Load and haul |  | Load and haul
Load and haul |  | 800t fleet - Flat
Load and haul | 8.12 | Load and haul 800 t fleet, flat, <1km | m3 | 3.5672
Load and haul | 8.13 | Load and haul 800 t fleet, flat, 1-2km | m3 | 4.2572
Load and haul | 8.14 | Load and haul 800 t fleet, flat, 2-5km | m3 | 5.546
Load and haul | 8.15 | Load and haul 800 t fleet, flat, >5km | m3 | 7.3557
Load and haul |  | 600t fleet -: Flat
Load and haul | 8.16 | Load and haul 600 t fleet, flat, <1km | m3 | 4.4004
Load and haul | 8.17 | Load and haul 600 t fleet, flat, 1-2km | m3 | 5.3117
Load and haul | 8.18 | Load and haul 600 t fleet, flat, 2-5km | m3 | 7.0041
Load and haul | 8.19 | Load and haul 600 t fleet, flat, >5km | m3 | 9.3736
Load and haul |  | 400t fleet - Flat
Load and haul | 8.2 | Load and haul 400 t fleet, flat, <1km | m3 | 4.5436
Load and haul | 8.21 | Load and haul 400 t fleet, flat, 1-2km | m3 | 5.7283
Load and haul | 8.22 | Load and haul 400 t fleet, flat, 2-5km | m3 | 7.4858
Load and haul | 8.23 | Load and haul 400 t fleet, flat, >5km | m3 | 10.0375
Load and haul |  | 800 t fleet - 50m Elevation
Load and haul | 8.24 | Load and haul 800 t fleet, 50m Elevation, <1km | m3 | 4.6087
Load and haul | 8.25 | Load and haul 800 t fleet, 50m Elevation, <1-2km | m3 | 5.546
Load and haul | 8.26 | Load and haul 800 t fleet, 50m Elevation, 2-5km | m3 | 6.7177
Load and haul | 8.27 | Load and haul 800 t fleet, 50m Elevation, >5km | m3 | 8.3972
Load and haul |  | 600 t fleet - 50m Elevation
Load and haul | 8.28 | Load and haul 600 t fleet, 50m Elevation, <1km | m3 | 5.7543
Load and haul | 8.29 | Load and haul 600 t fleet, 50m Elevation, <1-2km | m3 | 7.0041
Load and haul | 8.3 | Load and haul 600 t fleet, 50m Elevation, 2-5km | m3 | 8.5274
Load and haul | 8.31 | Load and haul 600 t fleet, 50m Elevation, >5km | m3 | 10.7275
Load and haul |  | 400 t fleet - 50m Elevation
Load and haul | 8.32 | Load and haul 400 t fleet, 50m Elevation, <1km | m3 | 6.3792
Load and haul | 8.33 | Load and haul 400 t fleet, 50m Elevation, <1-2km | m3 | 7.2906
Load and haul | 8.34 | Load and haul 400 t fleet, 50m Elevation, 2-5km | m3 | 8.8658
Load and haul | 8.35 | Load and haul 400 t fleet, 50m Elevation, >5km | m3 | 10.8317
Load and haul |  | 800 t fleet - 100m Elevation
Load and haul | 8.36 | Load and haul 800 t fleet, 100m Elevation, <1km | m3 | 5.8064
Load and haul | 8.37 | Load and haul 800 t fleet, 100m Elevation, <1-2km | m3 | 6.5875
Load and haul | 8.38 | Load and haul 800 t fleet, 100m Elevation, 2-5km | m3 | 7.7462
Load and haul | 8.39 | Load and haul 800 t fleet, 100m Elevation, >5km | m3 | 9.4257
Load and haul |  | 600 t fleet - 100m Elevation
Load and haul | 8.4 | Load and haul 600 t fleet, 100m Elevation, <1km | m3 | 7.3426
Load and haul | 8.41 | Load and haul 600 t fleet, 100m Elevation, <1-2km | m3 | 8.3581
Load and haul | 8.42 | Load and haul 600 t fleet, 100m Elevation, 2-5km | m3 | 9.8813
Load and haul | 8.43 | Load and haul 600 t fleet, 100m Elevation, >5km | m3 | 12.0815
Load and haul |  | 400 t fleet -100m Elevation
Load and haul | 8.44 | Load and haul 400 t fleet, 100m Elevation, <1km | m3 | 7.6941
Load and haul | 8.45 | Load and haul 400 t fleet, 100m Elevation, <1-2km | m3 | 8.8658
Load and haul | 8.46 | Load and haul 400 t fleet, 100m Elevation, 2-5km | m3 | 10.4411
Load and haul | 8.47 | Load and haul 400 t fleet, 100m Elevation, >5km | m3 | 12.394
Water | 9 | Water Management
Water | 9.01 | On-site treatment of contaminated water due to high salt (includes removal of metals etc., brine disposal and cost of mobile water treatment unit) | ML | 3050.6873
Water | 9.02 | On-site treatment of contaminated water due to low pH (incudes removal of metals etc., neutralisation treatments and cost of mobile water treatment unit | ML | 1699.738
Water | 9.03 | Small clean water dams (i.e. < 2ha) to be retained after mine closure – make safe and minor earthworks | @ | 3097.7834
Water | 9.03a | Large clean water dams (i.e. > 2 ha) to be retained after mine closure – make safe and minor earthworks | @ | 11827.9002
Water | 9.04 | Drain and remove sediments from the floor of the dam/pond prior to backfill or to enable it to be converted into clean water structure (haul distance <1km) | m3 | 4.5436
Water | 9.05 | Drain and remove sediments from the floor of the dam/pond prior to backfill or to enable it to be converted into clean water structure (haul distance >1km but <2km) | m3 | 5.7283
Water | 9.06 | Drain and remove sediments from the floor of the dam/pond prior to backfill or to enable it to be converted into clean water structure (haul distance >2km but <5km) | m3 | 7.4858
Water | 9.07 | Drain and remove sediments from the floor of the dam/pond prior to backfill or to enable it to be converted into clean water structure (haul distance >5km) | m3 | 10.0375
Water | 9.08 | Removal of evaporation fans and/or other water transfer and management infrastructure | @ | 28161.6672
Water | 10 | Creek Diversions
Water | 10.01 | Repairs and/or stabilisation of new or compromised water course diversion | m | 2768.2624
Water | 10.02 | Long term maintenance of water course diversion – Channel constructed through backfilled material | m | 1689.7
Water | 10.03 | Long term maintenance of water course diversion – Channel constructed through competent material | m | 844.85
Water | 10.04 | Installation of rock armouring | m2 | 8.2372
Sundry | 11 | Heritage Items
Sundry | 11.01 | The restoration and care and maintenance of heritage buildings / items that have local significance | allow | 14573.3471
Sundry | 11.02 | The restoration and care and maintenance of items that have historical significance - inspection and documentation of historical heritage items with no local significance i.e. per farming complex, cluster of historic mine openings, etc. | cluster | 3886.2259
Sundry | 11.03 | The restoration and care and maintenance of items that have historical significance - artefact placement | allow | 9715.5647
Sundry | 12 | HR, Admin and Sundry Items
Sundry | 12.01 | Stakeholder consultation during closure process | @ | N/A
Sundry | 12.02 | Development of an 'Unplanned' Project Closure Plan for imminent closure - Medium site | @ | 1943112.943
Sundry | 12.02a | Development of an 'Planned' Project Closure Plan | @ | 1018873.4431
Sundry | 12.02b | Development of an 'Unplanned' Project Closure Plan for imminent closure - Small site | @ | 971556.4715
Sundry | 12.02c | Development of an 'Unplanned' Project Closure Plan for imminent closure - Large site | @ | 2914669.4146
Holding | 12.05 | Permits required for mine closure activities | @ | 145733.4707
Sundry | 12.09 | Monitoring borehole installation | Item | 24288.9118
Sundry | 13 | Third Party Project Management and Contingencies
Indirects | 13.01 | Mobilisation & Demobilisation (Distance to site <150km) | item | 170096.47
Indirects | 13.02 | Mobilisation & Demobilisation (Distance to site >150km but <500km) | item | 292881.3391
Indirects | 13.03 | Mobilisation & Demobilisation (Distance to site >500km but <1000km) | item | 563233.3444
Indirects | 13.04 | Mobilisation & Demobilisation (Distance to site >1000km) | item | 765997.3484
Sundry | 13.05 | Contingency | Total | 0
Indirects | 13.06 | Post Closure Environmental Monitoring | Total | 9.716%
Indirects | 13.07 | Owners' Project Management and Surveying | Total | 9.716%
Holding | 14 | Holding Costs (costs per year after completion of rehabilitation execution to relinquishment). Refer holding costs tab |  | 0
Holding | 14.01 | Lease and licence Fees | Yr. | 0
Holding | 14.02 | Council rates / property taxes | Yr. | 0
Holding | 14.03 | Utilities (electricity, gas, potable water) | Yr. | 0
Holding | 14.04 | Obligations relating to ongoing statutory instruments | yr. | 0
Holding | 14.05 | Statutory reporting requirements (EPL returns, NPI etc.) | yr. | 0
Holding | 14.06 | Town / accommodation camp operating costs |  | 0
Holding | 14.07 | Site security | yr. | 0
Holding | 14.08 | Legal, consulting and professional fees | Yr. | 0
Holding | 14.09 | Access agreements | Yr. | 0
Holding | 14.1 | Repairs and maintenance | Yr. | 0
| 14.15 | Waste management and disposal. | Yr. | 0
| 14.16 | Labour | Yr. | 0
| 14.17 | WM recharge | Yr. | 0
Note on D80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These items are different for Qld - per ha rate for various road types
Note on D122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NSW rate now allows for grout filling at 7250 per LM