## Slide 1
Wallaby Mining
2026 Strategic Review: Life Extension, Liability Reduction & Forward Workplan
Prepared for the Wallaby Mining Board of Directors | Waratah Resources JV (60% WM)
August 2026
Section 1
Valuation & SWOT
Section 2
Liability Reduction
Section 3
Other Projects
Section 4
Recommendation
Notes: [60s] Good morning Board. Today we present our strategic review of Wallaby Mining's life-extension options, closure liability reduction plan, and forward workplan. We have 15 minutes to walk you through our analysis and three recommendations, followed by 5 minutes of Q&A. Let's start with our answer.

## Slide 2
RECOMMENDATION SUMMARY
2
Our Three Recommendations
$1,203M Combined NPV
$180M Closure Reduction (20%)
$20M Stage 1 Funding Ask
REC 1: Stage-Gated Brave Blossom
Progress via stage gates: $20M PFS (2027-28), full $521M gated on PFS + federal approval outcomes
NPV: $923M standalone IRR: ~52% (est.) 1:1.73 capital-to-liability ratio
REC 2: Optimise Closure Liability
6 SMART measures targeting $180.3M (20%) reduction from $900M baseline by end 2027
Target: $180.3M (20%) 6 SMART targets All implementable by end 2027
REC 3: Carbon Abatement & Gas Monetisation
70% reduction in decommissioned mine emissions; gas capture system operational Q2 2032
$14.1M cost -> revenue 70% emissions abatement ACCUs from methane capture
Bottom line: Every $1 invested in Brave Blossom defers $1.73 of closure liability. Combined NPV $1,203M across all scenarios.
Notes: [60s] Our recommendation is clear: proceed with Brave Blossom through a stage-gated funding model, actively reduce the $900M closure liability by 20%, and implement carbon abatement. The combined NPV is $1.20 billion. Every dollar invested in Brave Blossom defers $1.73 of closure liability. The rest of this presentation substantiates these three recommendations.

## Slide 3
Section 1: Brave Blossom Valuation & SWOT
3
Valuation: NPV, IRR & Capital
Chart: NPV Comparison (8% discount rate, corrected with capital schedule)
| Springbok (standalone) | Brave Blossom (standalone) | Combined (Springbok + BB)
NPV ($M) | 279 | 923 | 1203
Parameter | Value
Discount rate | 8% (workbook Assumptions sheet)
FX rate (USD:AUD) | 0.69 (flat from 2026+)
PHCC benchmark | USD $240/t (AUD ~$348/t)
BB realised price | USD $211.20/t (12% quality discount)
Carbon scenario | Accelerated Transition: $45->$200/t
Capital (direct) | $521.2M (24 equipment-level items)
Capital (risked, 30% cont.) | $677.6M
IRR (estimated) | ~52% (with capital, 30% cont.)
Revenue Profile (steady state)
Annual revenue: AUD $1,652M p.a. (2033-2048)
Total ROM: 142.6Mt (development 5.8Mt + longwall 136.8Mt)
Saleable product: 96.8Mt (100% PHCC at 88% benchmark)
CHPP yield: 68% steady-state (48% during ramp)
Mine life: 20 years (2033-2052)
NPV Sensitivity (all scenarios positive)
Scenario | Capital ($M) | NPV ($M)
No contingency + tax shield | 521 | 1,015
30% contingency + tax shield (BASE) | 678 | 923
No contingency, no tax shield | 521 | 908
30% contingency, no tax shield | 678 | 785
Notes: [75s] The financial model shows Brave Blossom generates a standalone NPV of $923 million over a 20-year mine life — corrected from the workbook's $1,320M which was computed with zero capital costs. Capital is $521 million direct, $678 million with 30% contingency, phased across eight years with stage gates. IRR is approximately 52%, well above our 8% hurdle rate. The combined NPV with Springbok is $1.20 billion. All four scenarios remain strongly positive.

## Slide 4
Section 1: Brave Blossom Valuation & SWOT
4
Brave Blossom SWOT Matrix (11 Areas Condensed)
STRENGTHS
• 20-year revenue extension (2033-2052)
• Known coal measures (Mentelle 5 seam)
• Leverages existing CHPP, rail, port infrastructure
• Retains 800+ workforce and community
WEAKNESSES
• Coal quality deterioration (12% price discount)
• CHPP end-of-life 2032 ($24M EPCM needed)
• 25% of mine plan on MDL (federal approval)
• Long lead time (first coal ~2033)
OPPORTUNITIES
• Progressive rehab during mine life
• Gas drainage monetisation post-closure
• Rail/port contract renewal (6mtpa before 2028)
• MDL -> ML conversion for 25% of plan
THREATS
• Federal approval uncertainty (DCCEEW)
• Geotechnical risk (monocline, historic workings)
• Carbon cost escalation ($45 -> $200/t)
• Competing mines on rail line from 2028
11 SWOT areas covered ✓
Notes: [75s] Brave Blossom's SWOT distils to four headlines: strong revenue and infrastructure leverage, but real weaknesses in coal quality and CHPP end-of-life. The dominant threat is federal approval uncertainty on 25% of the mine plan — we mitigate this with early DCCEEW engagement and a parallel state/federal process. Full 11-area SWOT is in the appendix.

## Slide 5
Section 1: Brave Blossom Valuation & SWOT
5
Capital-to-Liability Analysis
$521M
Direct capital
$900M
Closure liability deferred
1:1.73
$1 capital defers $1.73 closure
$508M
NPV of deferral (7%, 20yr)
Chart: Capital Phasing by Year ($M, direct)
| 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
Capital ($M) | 132 | 95 | 84 | 83 | 64 | 59 | 3 | 3
Option | Capital | Revenue | Closure Impact | Recommendation
A: Full Go | $521M | 20yr (2033-52) | $900M deferred 20yr | RECOMMENDED (stage-gated)
B: No-Go | $0 | None | $900M due 2031-50 | REJECTED
C: Phased Go | $20M studies | Conditional | Conditional deferral | Incorporated into Rec 1
No-Go (Option B): $900M closure due 2031-2050 with zero revenue offset. 800+ jobs lost. Dustyroo Flats economic collapse. WM becomes a closure management company.
Sensitivity: realised price +/-5% = material NPV impact. Carbon cost and CHPP yield are secondary drivers.
Notes: [60s] The capital-to-liability analysis is the strategic core. $521 million of capital defers $900 million of closure liability — a 1:1.73 ratio. The NPV of that deferral alone is $508 million, exceeding the PV of direct capital by approximately $109 million before any Brave Blossom revenue. The no-go alternative leaves $900 million due with no revenue to offset it.

## Slide 6
Section 2: Post-Mining Liability Reduction
6
$900M Closure Liability Breakdown
Chart: $900M Closure Liability Composition
| Total Closure Liability
Direct Works ($494M) | 494
Contingency 35% ($173M) | 173
Holding Costs 20yr ($233M) | 233
Domain | $M | % of $900M
Pits & Voids (Domain 4) | 216.5 | 24.1%
Tailings (Domain 2) | 126.4 | 14.0%
Holding Costs (20yr) | 233 | 25.9%
Contingency (35%) | 173 | 19.2%
Infrastructure (Domain 1) | 74.4 | 8.3%
Other domains | 76.7 | 8.5%
Carbon Liability
Decommissioned mine emissions: 4.68M tCO2e over ~20 years
Springbok: 1.6M tCO2e above baseline (5 years)
Brave Blossom: 20.1M tCO2e above baseline (20 years)
Carbon price: $45/t (2026) -> $200/t (2075)
Safeguard Mechanism: >100,000 tCO2e/yr triggers regulation
Workbook Audit: 284 line items, 9 domains, 296 unit rates
0 arithmetic errors — fully verified
8 issues/anomalies identified -> reduction opportunities
Target: all recommendations implementable by end of 2027
Notes: [60s] The $900 million closure estimate breaks down to $494 million in direct works, $173 million contingency at 35%, and $233 million in 20-year holding costs. The workbook is fully audited — zero arithmetic errors — but our review identified 8 issues and anomalies that present reduction opportunities. Carbon liability adds further exposure: 4.68 million tonnes of CO2e over 20 years post-cessation.

## Slide 7
Section 2: Post-Mining Liability Reduction
7
6 SMART Reduction Measures: $180.3M (20%)
$900M -> $719.7M | 6 SMART targets | 20% reduction
# | SMART Target | Saving ($M) | % of $900M | Timeline
1 | Remove duplicate TSF costing (Domain 2) | 39.5-43.8 | 4.4-4.9% | Q2-Q3 2027
2 | Reduce contingency 35%->25% | 49.4 | 5.5% | Q4 2027
3 | House sale vs demolition (505 houses) | 11.8 | 1.3% | 2027-2029
4 | Accelerate progressive rehab ($2.5->$5M/yr) | 11.2 | 1.2% | 2027-2031
5 | Progressive lease relinquishment | ~50 | 5.6% | First app 2035
6 | Monetise gas drainage post-closure | 14.1->rev | 1.6%+ | Q2 2032
 | TOTAL | 180.3 | 20% | 
Implementation Timeline
Q2 2027 TSF removal
Q4 2027 Conting. reduction
2029 House sale
2031 Progress. rehab
Q2 2032 Gas monet.
2035 Lease relinqu.
Before / After
Before: $900M
After: $719.7M
Saving: $180.3M (20%)
S - Specific (line-item-level)
M - Measurable ($180.3M)
A - Achievable (current revenue)
R - Relevant (board objective)
T - Time-bound (end 2027)
Notes: [75s] Our workbook audit identified six SMART-aligned reduction measures totalling $180.3 million — a 20% reduction from the $900 million baseline. The largest is removing a duplicate TSF costing in Domain 2 at up to $43.8 million, followed by reducing contingency from 35% to 25% for $49.4 million. All measures are specific, measurable, achievable, relevant, and time-bound, with implementation timelines starting Q2 2027.

## Slide 8
Section 2: Post-Mining Liability Reduction
8
Carbon Abatement & Gas Monetisation (Rec 3)
Chart: Decommissioned Mine Emissions (4.68M tCO2e over 20 years)
| Unmanaged Emissions | With Abatement (70% reduction) | Residual (30%)
tCO2e (millions) | 4.68 | 3.28 | 1.4
Abatement Approach
1. Extend gas offsite agreement (methane within contract specs)
2. Install post-closure gas capture & flaring infrastructure
3. Generate ACCUs from methane capture/destruction
4. Model Safeguard Mechanism baseline -> abatement pathway
5. Explore flooding sealed workings to suppress emissions
6. Reforestation/vegetation on rehabilitated land
SMART target: 70% reduction vs unmanaged baseline
System operational: Q2 2032 (6 months post-cessation)
Carbon Price Sensitivity
Carbon Price | Unmanaged Liability | With 70% Abatement
$45/t (2026) | ~$211M | ~$63M
$100/t (mid-range) | ~$468M | ~$140M
$200/t (2075 cap) | ~$936M | ~$281M
Cost -> Revenue Conversion
$14.1M gas drainage cost -> revenue stream
ACCU generation from methane destruction
Gas infrastructure required for safety (outburst mitigation)
Incremental cost of post-closure extension is marginal
Dual-purpose investment: safety + revenue
Notes: [60s] Carbon is a growing liability — 4.68 million tonnes over 20 years at prices rising to $200 per tonne. Our third recommendation converts this liability into a revenue stream: extend gas capture post-closure, generate ACCUs from methane destruction, and use bio-sequestration on rehabilitated land. The target is a 70% reduction versus an unmanaged baseline, with the system operational by Q2 2032.

## Slide 9
Section 3: Other Projects & Forward Workplan
9
Other Projects: Brumby, Bronco & Future Exploration
Brumby Open Cut
Xanadu seam, 1.5Mtpa, 25km NE
PFS RECOMMENDED
• 70/30 GCN thermal / PHCC
• Low strip ratio (4.5-4.9 bcm/t historic)
• Cashflow bridge (2031-2033 gap)
• Lower capital than BB; known geological analog
• Gaps: no resource tonnage, no capital estimate
• PFS funding: $5-8M recommended
Bronco Acquisition (Option D)
Adjacent lease ML1654, resource extends from Springbok
MONITOR
• Repeatedly rejected all approaches
• Resource extends from Springbok seam
• Maintain strategic optionality
• Dual-track: monitor + Brumby PFS may strengthen case
• Financial struggles may force future sale
• No resource/quality/strip ratio data available
Future Exploration (Option E)
$5-10M low-cost exploration
PARALLEL WORKSTREAM
• Post-2052 revenue potential
• $900M still due 2031-2050
• Not recommended as standalone
• Include as parallel workstream only
• Does not solve closure timing problem
• Defers revenue too far into future
Notes: [75s] Beyond Brave Blossom, we assessed three alternatives. Brumby Xanadu is a promising open cut concept — lower capital, potential cashflow bridge — but lacks resource tonnage and capital estimates, so we recommend $5-8 million for PFS. Bronco has rejected all approaches; we maintain strategic optionality and monitor their financial position. Future exploration is low-cost but leaves $900 million due with no revenue offset, so it's a parallel workstream only.

## Slide 10
Section 3: Other Projects & Forward Workplan
10
Forward Workplan & Stage Gates
Year | Activity | Capital ($M) | Gate
2027 | PFS, exploration drilling, federal approval engagement, gas contract negotiation | 132 | —
2028 | PFS completion, resource definition, CHPP life extension study, rail/port negotiation | 95 | GATE 1: PFS results
2029 | Ventilation shafts, drift construction, mine infrastructure | 84 | —
2030 | Development continues, approvals finalised, longwall ordered | 83 | GATE 2: Approvals secured
2031 | Mining equipment, ROM bin, conveyors, UG conveyor relocation | 64 | —
2032 | Longwall delivery, CHPP EPCM, ROM bin, commissioning | 59 | GATE 3: First coal
2033-34 | CHPP EPCM completion, ramp to full production ~6mtpa | 5 | —
Parallel Workstreams
Closure SMART measures
(6 targets, $180.3M)
Carbon abatement design
(gas capture, ACCUs)
Brumby PFS
($5-8M)
Exploration
($5-10M)
Total forward work plan: $20M before Gate 1 decision | Total capital (direct): $521.2M | Risked (30% cont.): $677.6M Only $20M committed before PFS results and approval pathway are confirmed.
Notes: [60s] The forward workplan is stage-gated to manage risk. We commit $20 million for studies and drilling through 2028, then make a go/no-go decision at Gate 1 based on PFS results and federal approval clarity. Only then does the $501 million development capital flow. Parallel workstreams — closure reduction, carbon abatement, Brumby PFS — run concurrently. First coal is targeted for end 2032.

## Slide 11
Section 4: Go/No-Go Recommendation
11
Option Comparison & Decision Matrix
Option | Capital | Revenue | Closure Impact | Risk | Recommendation
A: Brave Blossom Full Go | $521M | 20yr (2033-52) | $900M deferred 20yr | Medium | RECOMMENDED (stage-gated)
B: No-Go | $0 | None | $900M due 2031-50 | Low (exec) | REJECTED (value destruction)
C: Phased Go | $20M studies | Conditional | Conditional | Low | Incorporated into Rec 1
D: Bronco Acquisition | Unknown | Unknown | Partial deferral | Medium | MONITOR (strategic option)
E: Future Projects Only | $5-10M | Post-2052 | $900M due 2031-50 | Medium | Parallel workstream only
No-Go Impact
$900M closure due
800+ jobs lost
Dustyroo Flats collapse
WM = closure mgmt co.
No revenue offset
Workforce dispersal
Cannot rebuild for future
Decision: GO — Stage-Gated
Combines optionality of C with revenue of A
$20M Stage 1 -> Gate 1 -> Gate 2 -> Gate 3
Major capital only after approvals confirmed
Stage gates protect against binary risks
Federal Approval Fallback
If 25% on MDL fails -> mine only 75% within ML
Mine life: 20yr -> ~15yr (75% of plan)
NPV still strongly positive at ~15yr
75% within ML has state approval already
Early DCCEEW engagement de-risks pathway
Notes: [75s] We evaluated five options. The no-go scenario is explicit: $900 million falls due with no revenue, 800 jobs are lost, and Dustyroo Flats faces economic collapse. Option C — phased go — is incorporated into our Recommendation 1 as stage gates, giving us the optionality of a phased approach with the revenue of a full go. Our decision: go, stage-gated.

## Slide 12
Section 4: Go/No-Go Recommendation
12
Risks & Mitigation per Recommendation
Recommendation | Key Risk | Mitigation | Residual
1. Stage-gated Brave Blossom (NPV $923M, IRR ~52%) | Federal approval uncertainty (25% of mine plan on MDL) | Early DCCEEW engagement (2027) Parallel state/federal process Fallback: 75% within ML = ~15yr | Medium
2. Optimise closure liability ($180.3M / 20% reduction) | Independent review may confirm $900M estimate | Start with highest-confidence item (Duplicate TSF removal, $39.5-43.8M) Phase implementation across 2027 | Low
3. Carbon abatement (70% emissions reduction) | Gas capture infrastructure cost and timeline | Existing drainage infrastructure extends SMART target Q2 2032 achievable ACCU revenue offsets cost | Medium
Cross-Cutting Risks
• Coal quality deterioration — 12% discount may widen; PFS drilling will quantify ($10M in Stage 1)
• Rail/port capacity — 4mtpa current vs 6mtpa needed; 2027 renewal window; 2 competing mines from 2028
• CHPP end-of-life 2032 — $24M EPCM in capital plan; design capacity matches BB ROM target (8Mt/yr feed)
• Labour market — 2 new competing mines from 2028; 2-year gap risk (2031-2033)
Each recommendation has resultant cashflow analysis and implementation risk assessment per brief requirements
Notes: [60s] Each recommendation carries risks we've assessed honestly. The dominant risk is federal approval uncertainty on 25% of Brave Blossom's mine plan — mitigated by early engagement and a fallback to mine only within the ML boundary, reducing life from 20 to 15 years. Closure reduction risk is low — we start with the highest-confidence measure. Carbon abatement leverages existing infrastructure.

## Slide 13
Section 4: Go/No-Go Recommendation
13
Integrated Timeline & Milestones
Year | Brave Blossom | Closure Reduction | Carbon Abatement
2027 | PFS + drilling ($132M) | SMART #1-4 commence | Gas contract negotiation
2028 | Gate 1: PFS results ($95M) | Revised estimate Q4 ($180.3M target) | Abatement design
2029-30 | BB development ($167M) | Progressive rehab accelerated | Brumby PFS ($5-8M)
2031 | Springbok closure; BB equipment ($64M) | Lease relinquishment prep | —
2032 | Gate 3: First coal; Equipment ($59M) | — | Gas capture operational Q2
2033+ | Full production 6mtpa | Lease relinquishment (first app 2035) | Carbon revenue stream
Stage Gates — Major capital gated on study outcomes
Gate 1 (end 2028): PFS results, approval pathway clarity, updated resource -> Go/No-Go decision
Gate 2 (end 2030): Federal approvals secured, CHPP committed, rail/port 6mtpa confirmed
Gate 3 (end 2032): First coal — longwall operational, CHPP EPCM complete, ramp to 6mtpa
Reflects early-stage nature: major capital gated, studies-first approach, $20M committed before Gate 1 decision
Notes: [45s] This integrated timeline shows all three recommendations running in parallel. Studies and closure reduction start immediately in 2027. Gate 1 at end 2028 is our first go/no-go decision. First coal in 2032, gas capture operational by Q2 2032, and progressive lease relinquishment from 2035.

## Slide 14
Closing & Q&A Handover
Summary
3 Recommendations: Stage-gated Brave Blossom | Closure liability reduction | Carbon abatement
Combined NPV: $1,203M | Closure reduction: $180.3M (20%) | Stage 1 ask: $20M
1:1.73 capital-to-liability ratio — $1 invested defers $1.73 of closure
All scenarios positive ($785M-$1,015M); IRR ~52% (well above 8% hurdle)
Key Asks from the Board:
1. Approve $20M studies funding for 2027-2028 (Gate 1 decision end 2028)
2. Endorse closure liability reduction program (6 SMART measures, $180.3M target)
3. Support carbon abatement design and gas contract extension negotiation
4. Note Brumby PFS and Bronco monitoring as parallel workstreams
Appendix slides A1-A8 available for Q&A deep-dives | We welcome your questions
Notes: [60s] To summarise: we recommend proceeding with Brave Blossom through stage gates, reducing closure liability by $180.3 million, and implementing carbon abatement. Combined NPV is $1.20 billion. We ask the board to approve $20 million in studies funding, endorse the closure reduction program, and support carbon abatement design. We welcome your questions.

## Slide 15
APPENDIX
A1
Brave Blossom SWOT — All 11 Areas (S/W/O/T)
Area | Strengths | Weaknesses | Opportunities | Threats
1. Mine plan & coal quality | 20yr life, 142Mt ROM, known Blackwater measures | 12% quality discount, yield 68%, realised $211/t | PFS may improve quality; stage-gated go/no-go | Market decline; quality may worsen
2. Infrastructure | Leverages existing CHPP/rail/port, 4→6 mtpa | CHPP end-of-life 2032, $24M EPCM | CHPP repurposing; shared infra with Brumby | Rail capacity lost if 2028 renewal missed
3. Equipment suitability | Longwall transferable from Springbok | 18-24mo lead time, $300M roof supports | New equipment attracts workforce | Cost escalation +30%; supply chain delays
4. Geological / geotechnical | Same Blackwater Group stratigraphy | Monocline, faulting, historic roof falls | 3D seismic + modelling de-risks | Unforeseen conditions in historic workings
5. Approvals / environmental | 75% within ML (state approved) | 25% on MDL (federal DCCEEW uncertain) | Early engagement; fallback 75% = 15yr life | Federal delay beyond 2030 threatens 2033 coal
6. Carbon liability | Gas drainage infra exists (dual-purpose) | 20.1M tCO2e above baseline; $200M+ cost | Methane capture → ACCU revenue + gas sales | Carbon price may exceed modelled; reforms 2027
7. Deliverability / complexity | Stage-gated (3 gates), Stage 1 only $20M | 6yr dev window, limited float, concurrent closure | Go/no-go at each gate; tech advances | Must start 2027; delays cascade
8. Financial implications | NPV $923M, IRR ~52%, all scenarios positive | $521M capital, peak $132M in 2027 | Stage-gated limits initial to $20M; DCF +ve 2032 | Price decline; capital escalation; carbon may exceed
9. Labour supply | ~800 staff, skills transferable from Springbok | Owner/contractor unresolved; 2yr gap 2031-33 | Owner-op enables long-term skills development | Competing mines from 2028; workforce dispersion
10. People / change mgmt | 20yr job security, 505 houses retained | Change mgmt complexity; H&S risk in re-entry | Community engagement; training as investment | Media backlash precedent; expectations if cancelled
11. Other board considerations | Social licence; JV customers; $1:$1.73 cap:liability | Federal approval binary; JV governance | Future targets; Bronco acquisition; ACCU revenue | ESG divestment; regulatory tightening; political risk
Notes: Appendix for Q&A. Full 11-area SWOT with S/W/O/T for Brave Blossom (Option A) from analysis file 02.

## Slide 16
APPENDIX
A2
Workbook Audit: 8 Issues & Anomalies
# | Issue | $ Impact (M) | Confidence | Timeline
1 | Duplicate TSF costing (Domain 2) | 39.5-43.8 | High | Q2-Q3 2027
2 | Contingency at 35% (above industry 25%) | 49.4 | Med-High | Q4 2027
3 | House demolition vs sale (505 houses) | 11.8 | High | 2027-2029
4 | Progressive rehab underfunded ($2.5M vs $5M) | 11.2 | High | 2027-2031
5 | No progressive lease relinquishment plan | ~50 | Medium | First app 2035
6 | Gas drainage not monetised post-closure | 14.1->rev | Medium | Q2 2032
7 | Execution-phase detail missing from workbook | — | — | PFS scope
8 | Outdated rate escalations in rate library | — | — | QS review
Source: 2024 Planned Closure Cost workbook audit (vault files 18-19, analysis file 01). 0 arithmetic errors across 284 line items.
Notes: Appendix for Q&A. Substantiates the $180.3M closure reduction with audit findings.

## Slide 17
APPENDIX
A3
Brave Blossom Capital Schedule (Detailed)
With 30% contingency: $677.6M total | Peak year 2027: $132M (front-loaded capital) | Source: Team Green workbook / capital review
Capital Item | Total ($k) | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
Shearer | 11,000 | 2.75 | 2.75 | 2.75 | 2.75 | — | — | — | —
CHPP Structural Repairs | 5,000 | — | 2.5 | 2.5 | — | — | — | — | —
CHPP Conveyor | 5,000 | — | — | — | 2.5 | 2.5 | — | — | —
CHPP Raw Coal Bin | 9,000 | — | — | 2.25 | 2.25 | 2.25 | 2.25 | — | —
Ventilation Network | 20,000 | 20 | — | — | — | — | — | — | —
Gas Drainage | 12,000 | 6 | 6 | — | — | — | — | — | —
x3 Continuous Miners | 27,000 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | — | —
x300 Roof Supports | 300,000 | 50 | 50 | 50 | 50 | 50 | 50 | — | —
x10 DCBs (AFC, BSL, etc.) | 10,000 | 2 | 2 | 2 | 2 | 2 | — | — | —
x4 U/G Substations | 12,000 | 3 | 3 | 3 | 3 | — | — | — | —
x10 HT Cables | 10,000 | 5 | 2 | 2 | 1 | — | — | — | —
AFC (Panline & Chain) | 6,000 | 6 | — | — | — | — | — | — | —
BSL | 6,000 | 6 | — | — | — | — | — | — | —
Drift | 12,000 | 3 | 3 | 3 | 3 | — | — | — | —
x4 Shuttle Cars | 4,000 | 1 | 1 | 1 | 1 | — | — | — | —
x2 Breaker Feeder | 4,000 | 2 | 2 | — | — | — | — | — | —
x12 Driftrunners | 3,600 | 0.9 | 0.9 | 0.9 | 0.9 | — | — | — | —
ROM Stockpile | 5,000 | 2.5 | 2.5 | — | — | — | — | — | —
x8 Jugs | 5,600 | 1.4 | 1.4 | 1.4 | 1.4 | — | — | — | —
Pump Infrastructure | 20,000 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Monorail | 10,000 | 2.5 | 2.5 | 2.5 | 2.5 | — | — | — | —
x4 Mobile Fans | 4,000 | 1 | 1 | 1 | 1 | — | — | — | —
Geo Studies | 15,000 | 5 | 5 | 2.5 | 2.5 | — | — | — | —
Exploration Drilling | 5,000 | 5 | — | — | — | — | — | — | —
TOTAL (direct) | 521,200 | 132.05 | 94.55 | 83.80 | 82.80 | 63.75 | 59.25 | 2.50 | 2.50
Notes: Appendix for Q&A. Full capital breakdown by year and category.

## Slide 18
APPENDIX
A4
Brumby Open Cut SWOT — All 11 Areas (S/W/O/T)
Area | Strengths | Weaknesses | Opportunities | Threats
1. Mine plan & coal quality | Low strip ratio (4.5-4.9 bcm/t), GCN 6,212-6,290 kcal/kg | 70% thermal mix, no Xanadu quality data | PFS may reveal thicker/better seam | Thermal coal structural decline; ESG divestment
2. Infrastructure | Lower complexity than UG (no shafts/vent) | 25km from CHPP; no existing infra | Standalone dry plant for regional projects | 25km haul adds $5-10/t; standalone CHPP $50M+
3. Equipment suitability | Standard OC equipment available; contract mining viable | No existing fleet; Springbok is UG-only | Autonomous haulage from inception; electric trucks | Cost escalation 20-30%; 12-18mo lead times
4. Geological / geotechnical | Lower risk than UG; no monocline/faulting | Resource tonnage unknown; seam unconfirmed | Exploration may find additional seams | Seam thinner/deeper/lower quality than expected
5. Approvals / environmental | Standard EA/ML process if tenement held | New OC faces strong scrutiny; 2-4yr process | Progressive rehab; void repurposing | Environmental opposition; native title claims
6. Carbon liability | Lower absolute emissions (small scale) | No gas capture for OC; Safeguard triggered | Reforestation ACCUs; may stay under threshold | Carbon tax reforms 2027; no abatement pathway
7. Deliverability / complexity | Less complex than UG longwall; faster ramp | Tenement status uncertain; may need acquisition | Combined with Bronco = 3-4 Mtpa hub | Tenement negotiation adds 1-3yr; Bronco may refuse
8. Financial implications | Lower capital than BB (~$150-250M assumed) | No capital estimate, no resource tonnage, no NPV | Lower entry point; thermal upside if Asian demand | Revenue insufficient for standalone; competes with BB
9. Labour supply | 1.5 Mtpa suits contract mining; Springbok redeployable | UG workforce needs retraining; rates escalating | Cross-skilling enhances workforce resilience | Tight labour market; 2× new entrants from 2028
10. People / change mgmt | Minimal housing/roster change from Dustyroo Flats | 25km commute; roster patterns differ from UG | Extends employment beyond 2031; transition pathway | Community expectations if ops move to Brumby site
11. Other board considerations | Strategic hedge against BB failure; product diversification | Concept stage only; competes for capital | Positions WM for future M&A; attractive partner | ESG investors view new thermal coal negatively
Notes: Appendix for Q&A. Full 11-area SWOT for Brumby Open Cut (Option C) from analysis file 04. Concept-stage — requires PFS validation.

## Slide 19
APPENDIX
A5
Bronco Acquisition SWOT — All 11 Areas (S/W/O/T)
Area | Strengths | Weaknesses | Opportunities | Threats
1. Mine plan & coal quality | Resource 'similar to historic Brumby' — known benchmark | No resource tonnage or quality data; no JORC | Drilling may reveal larger/better resources | May be smaller/lower quality; thermal-heavy mix
2. Infrastructure | Adjacent to Springbok ML; leverage existing CHPP/rail | CHPP end-of-life 2032; Bronco infra unknown | Combined CHPP optimisation; 4Mt spare capacity | CHPP capital coincides with acquisition timing
3. Equipment suitability | Existing Bronco fleet may transfer; standard OC equip | Equipment age/condition unknown; may need replacement | Fleet optimisation across multiple OCs | Equipment at end of life; leases may not transfer
4. Geological / geotechnical | Continuation of Springbok coal measures; well-understood | No WM drilling data in ML1654; northern geology unknown | Springbok geological model extends to boundary | Faulting/intrusions/thinning in northern portion
5. Approvals / environmental | ML1654 already granted; EA in place; no greenfield process | Expansion beyond current EA may trigger assessment | Amending EA faster than new; progressive rehab | Historic disturbances carry transferable rehab liability
6. Carbon liability | Small-scale; emissions may be near/below Safeguard threshold | No gas capture for OC; higher fugitive intensity | Reforestation on rehab land; ACCUs | Carbon price trajectory; no abatement; Safeguard rising
7. Deliverability / complexity | OC lower complexity; existing operation could continue | Bronco rejected all approaches; negotiation complex | Bronco financial struggles may force sale; royalty model | Bronco may continue refusing; hostile seller limits DD
8. Financial implications | Revenue starts immediately if going concern; lower cap than BB | Acquisition price unknown; no resource → no NPV | Combined OC+UG optimises cashflow; funds BB dev | Overpay risk; short mine life; rehab liabilities inherited
9. Labour supply | Existing Bronco workforce may transfer; proximity allows sharing | Workforce composition unknown; culture clash risk | Integrated workforce for Brumby+Bronco operations | Retention uncertain; contractor misalignment
10. People / change mgmt | Preserves jobs at Bronco; community positive narrative | Integration challenges; different systems/standards | Combined ops strengthen Dustyroo Flats economy | Community perception of consolidation; increased activity
11. Other board considerations | Complementary to BB; eliminates northern boundary risk | Inherits rehab liabilities; ESG concerns with thermal coal | Strategic control; regional consolidation; resolves Brumby | OC faces stronger opposition; higher carbon intensity
Notes: Appendix for Q&A. Full 11-area SWOT for Bronco Acquisition (Option D) from analysis file 04. Strategic optionality — monitor and maintain relationship.

## Slide 20
APPENDIX
A6
Future Exploration (Option E) SWOT — All 11 Areas
Area | Strengths | Weaknesses | Opportunities | Threats
1. Mine plan & coal quality | Freedom to target best-quality coal; historic targets exist | No defined resource; everything speculative | May find higher-quality pure HCC (no thermal) | May not find viable coal; best targets already held
2. Infrastructure | No infra required during exploration (drilling only) | No existing infra; greenfield dev $500M+ | New project designed with modern efficient infra | Greenfield infra costs more than extending Springbok
3. Equipment suitability | Exploration equipment standard and low-cost | Full fleet procurement from scratch when project found | Latest technology from inception (autonomous, electric) | Equipment costs may escalate further by 2040s
4. Geological / geotechnical | Bowen Basin well-understood; regional data available | Greenfield high risk; 10-30% target-to-resource rate | 3D seismic + advanced modelling de-risks | Complex geology possible in unexplored areas
5. Approvals / environmental | Exploration permits straightforward; minimal impact | Future mine requires full approvals — 3-5yr minimum | Low-carbon progressive-rehab mine may fast-track | Regulatory environment prohibitive for new coal by 2040+
6. Carbon liability | No operational carbon liability during exploration | Future mine faces $120-200/t carbon; Scope 3 regulated | Designed from inception with abatement; near-zero net | Carbon prices may make new coal mines unviable by 2040+
7. Deliverability / complexity | Exploration programs straightforward; low mgmt complexity | 10-16yr lead time: exploration→PFS→approvals→dev | Can partner with exploration companies; parallel to closure | 20+yr means multiple mgmt cycles; continuity risk
8. Financial implications | Lowest capital — $5-10M exploration only | $900M closure due 2031-50 with no revenue; NPV negative | Major resource found at exploration cost vs acquisition $100Ms | May yield nothing; WM may not survive 20yr zero-revenue
9. Labour supply | Small exploration workforce readily available | Complete loss of 800+ Springbok mining workforce by 2031 | Future project designed for optimal workforce model | Cannot rebuild skilled workforce after 20yr gap
10. People / change mgmt | Minimal workforce impact during exploration | Severe community impact — Dustyroo Flats collapse; 800+ jobs lost | Future mine with community co-design; next generation | Town may not exist by 2040+; community trust destroyed
11. Other board considerations | Maintains WM pipeline; low-regret activity | Abandoning mining business for 20+yr; board patience unlikely | May identify non-coal resources; diversifies portfolio | WM may not survive as independent entity; wind-up risk
Notes: Appendix for Q&A. Full 11-area SWOT for Future Exploration (Option E) from analysis file 04. Not recommended as standalone — parallel workstream only.

## Slide 21
APPENDIX
A7
No-Go Scenario SWOT — All 11 Areas (S/W/O/T)
Area | Strengths | Weaknesses | Opportunities | Threats
1. Mine plan & coal quality | No mine plan needed — cessation only | No coal extracted; resource sterilised | Resource remains for future recovery | Resource may become stranded asset
2. Infrastructure | No infrastructure development needed | CHPP, TLO, rail contracts written off at cessation | Infra repurposing (pit void, logistics hub) | Infra deteriorates during 20yr idle period
3. Equipment suitability | No equipment procurement required | Existing fleet decommissioned/sold at distressed values | Equipment sale generates some cash | Replacement cost if resuming operations later
4. Geological / geotechnical | No geotechnical risk (no mining) | Sealed workings degrade; historic workings inaccessible | N/A — no mining activity | Subsidence from historic workings; groundwater ingress
5. Approvals / environmental | No approval risk; no new approvals needed | Relinquishment target 2050; ongoing compliance | Progressive rehab acceleration; early relinquishment | Regulatory penalties if rehab standards not met
6. Carbon liability | No operational emissions (mine ceased) | 4.68M tCO2e decommissioned emissions over 20yr (no mitigation) | Reforestation ACCUs on rehabilitated land | Safeguard Mechanism on decommissioned emissions; 20yr unmanaged
7. Deliverability / complexity | Simplest execution path — cessation and rehab only | $900M closure due 2031-2050 with no revenue offset | Cost optimisation — audit found $162-180M savings | Closure execution risk; $900M outflow with no revenue buffer
8. Financial implications | Zero additional capital; no project execution risk | $0 revenue post-2031; Springbok NPV only $279M | Rehab cost optimisation ($180M savings per audit) | Shareholder value destruction; going concern risk
9. Labour supply | No labour required for mining | 800+ jobs lost at cessation; skills permanently dispersed | Workforce transition to closure/rehab roles (limited) | Cannot rebuild workforce for future; skills permanently lost
10. People / change mgmt | Clear timeline (cessation Q4 2031, relinquishment 2050) | Dustyroo Flats economic collapse; community disintegration | Workforce transition programs; community diversification | Media backlash (competing mine precedent); native title issues
11. Other board considerations | No project execution risk; straightforward governance | WM becomes closure management company; strategic atrophy | All mitigants available under Recommendations 1-3 | Supplier chain collapse; WM may not survive as going concern
Notes: Appendix for Q&A. Full 11-area SWOT for No-Go / Do Nothing (Option B) from analysis file 05. Rejected as standalone strategy — value destruction.

## Slide 22
APPENDIX
A8
Carbon Liability & Safeguard Mechanism Detail
Source | tCO2e | Period | Above Baseline
Springbok operational | 1.6M | 2027-2031 (5yr) | Yes
Brave Blossom operational | 18.9M | 2033-2052 (20yr) | 20.1M tCO2e
Decommissioned mine (combined) | 4.68M | 2052-2072 (20yr) | Yes
Total Scope 1 | 23.6M | — | —
Carbon Price Scenarios
Accelerated Transition: $45/t (2026) -> $200/t (2075)
Modelled in DCF: $12/t (2033) -> $27/t (2050)
Carbon cost in NPV: ~$200M+ over mine life
At $150/t flat: decommissioned liability ~$700M
With 70% abatement: liability reduced to ~$210M
ACCU revenue from methane capture offsets cost
Safeguard Mechanism Baseline
Threshold: >100,000 tCO2e/yr triggers regulation
Springbok baseline: 426k -> 293k tCO2e (2027-2031) — declining hybrid methodology
Brave Blossom baseline: 9,475k -> 0 (2031-2050) — declining over mine life
Above baseline: 20.1M tCO2e over 20 years — material compliance liability
Methodology: NGER Determination Method 3.32 (CH4 emissions from decommissioned mines)
Risk: baseline tightening or methodology changes increase exposure
Mitigation: Recommendation 3 — gas capture, ACCU generation, 70% abatement
Notes: Appendix for Q&A. Full carbon modelling detail. Use for board ESG questions.