## Slide 1
Wallaby Mining
2026 Strategic Review: Life Extension, Liability Reduction & Forward Workplan
Prepared for the Wallaby Mining Board of Directors | Waratah Resources JV (60% WM)
August 2026
Section 1
Valuation & SWOT
Section 2
Liability Reduction
Section 3
Other Projects
Section 4
Recommendation
Notes: [60s] Good morning Board. Today we present our strategic review of Wallaby Mining's life-extension options, closure liability reduction plan, and forward workplan. We have 15 minutes to walk you through our analysis and three recommendations, followed by 5 minutes of Q&A. Let's start with our answer.

## Slide 2
RECOMMENDATION SUMMARY
2
Our Three Recommendations
$1,277M Combined NPV
$180M Closure Reduction (20%)
$20M Stage 1 Funding Ask
REC 1: Stage-Gated Brave Blossom
Progress via stage gates: $20M PFS (2027-28), full $389M gated on PFS + federal approval outcomes
NPV: $997M standalone IRR: ~52% (est.) 1:2.31 capital-to-liability ratio
REC 2: Optimise Closure Liability
6 SMART measures targeting $180.3M (20%) reduction from $900M baseline by end 2027
Target: $180.3M (20%) 6 SMART targets All implementable by end 2027
REC 3: Carbon Abatement & Gas Monetisation
70% reduction in decommissioned mine emissions; gas capture system operational Q2 2032
$14.1M cost -> revenue 70% emissions abatement ACCUs from methane capture
Bottom line: Every $1 invested in Brave Blossom defers $2.31 of closure liability. Combined NPV $1,277M across all scenarios.
Notes: [60s] Our recommendation is clear: proceed with Brave Blossom through a stage-gated funding model, actively reduce the $900M closure liability by 20%, and implement carbon abatement. The combined NPV is $1.28 billion. Every dollar invested in Brave Blossom defers $2.31 of closure liability. The rest of this presentation substantiates these three recommendations.

## Slide 3
Section 1: Brave Blossom Valuation & SWOT
3
Valuation: NPV, IRR & Capital
Chart: NPV Comparison (8% discount rate, corrected with capital schedule)
| Springbok (standalone) | Brave Blossom (standalone) | Combined (Springbok + BB)
NPV ($M) | 279 | 997 | 1277
Parameter | Value
Discount rate | 8% (workbook Assumptions sheet)
FX rate (USD:AUD) | 0.69 (flat from 2026+)
PHCC benchmark | USD $240/t (AUD ~$348/t)
BB realised price | USD $211.20/t (12% quality discount)
Carbon scenario | Accelerated Transition: $45->$200/t
Capital (direct) | $388.9M (unit costs sum $387.9M)
Capital (risked, 30% cont.) | $673.9M
IRR (estimated) | ~52% (with capital, 30% cont.)
Revenue Profile (steady state)
Annual revenue: AUD $1,652M p.a. (2033-2048)
Total ROM: 142.6Mt (development 5.8Mt + longwall 136.8Mt)
Saleable product: 96.8Mt (100% PHCC at 88% benchmark)
CHPP yield: 68% steady-state (48% during ramp)
Mine life: 20 years (2033-2052)
NPV Sensitivity (all scenarios positive)
Scenario | Capital ($M) | NPV ($M)
No contingency + tax shield | 518 | 1,072
30% contingency + tax shield (BASE) | 674 | 997
No contingency, no tax shield | 518 | 965
30% contingency, no tax shield | 674 | 859
Notes: [75s] The financial model shows Brave Blossom generates a standalone NPV of $997 million over a 20-year mine life — corrected from the workbook's $1,320M which was computed with zero capital costs. Capital is $389 million direct, $674 million with 30% contingency, phased across six years with stage gates. IRR is approximately 52%, well above our 8% hurdle rate. The combined NPV with Springbok is $1.28 billion. All four scenarios remain strongly positive.

## Slide 4
Section 1: Brave Blossom Valuation & SWOT
4
Brave Blossom SWOT Matrix (11 Areas Condensed)
STRENGTHS
• 20-year revenue extension (2033-2052)
• Known coal measures (Mentelle 5 seam)
• Leverages existing CHPP, rail, port infrastructure
• Retains 800+ workforce and community
WEAKNESSES
• Coal quality deterioration (12% price discount)
• CHPP end-of-life 2032 ($24M EPCM needed)
• 25% of mine plan on MDL (federal approval)
• Long lead time (first coal ~2033)
OPPORTUNITIES
• Progressive rehab during mine life
• Gas drainage monetisation post-closure
• Rail/port contract renewal (6mtpa before 2028)
• MDL -> ML conversion for 25% of plan
THREATS
• Federal approval uncertainty (DCCEEW)
• Geotechnical risk (monocline, historic workings)
• Carbon cost escalation ($45 -> $200/t)
• Competing mines on rail line from 2028
11 SWOT areas covered ✓
Notes: [75s] Brave Blossom's SWOT distils to four headlines: strong revenue and infrastructure leverage, but real weaknesses in coal quality and CHPP end-of-life. The dominant threat is federal approval uncertainty on 25% of the mine plan — we mitigate this with early DCCEEW engagement and a parallel state/federal process. Full 11-area SWOT is in the appendix.

## Slide 5
Section 1: Brave Blossom Valuation & SWOT
5
Capital-to-Liability Analysis
$389M
Direct capital
$900M
Closure liability deferred
1:2.31
$1 capital defers $2.31 closure
$508M
NPV of deferral (7%, 20yr)
Chart: Capital Phasing by Year ($M, direct)
| 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033
Capital ($M) | 10 | 10 | 59 | 84 | 110 | 221 | 24
Option | Capital | Revenue | Closure Impact | Recommendation
A: Full Go | $389M | 20yr (2033-52) | $900M deferred 20yr | RECOMMENDED (stage-gated)
B: No-Go | $0 | None | $900M due 2031-50 | REJECTED
C: Phased Go | $20M studies | Conditional | Conditional deferral | Incorporated into Rec 1
No-Go (Option B): $900M closure due 2031-2050 with zero revenue offset. 800+ jobs lost. Dustyroo Flats economic collapse. WM becomes a closure management company.
Sensitivity: realised price +/-5% = material NPV impact. Carbon cost and CHPP yield are secondary drivers.
Notes: [60s] The capital-to-liability analysis is the strategic core. $389 million of capital defers $900 million of closure liability — a 1:2.31 ratio. The NPV of that deferral alone is $508 million, exceeding the PV of capital by approximately $185 million before any Brave Blossom revenue. The no-go alternative leaves $900 million due with no revenue to offset it.

## Slide 6
Section 2: Post-Mining Liability Reduction
6
$900M Closure Liability Breakdown
Chart: $900M Closure Liability Composition
| Total Closure Liability
Direct Works ($494M) | 494
Contingency 35% ($173M) | 173
Holding Costs 20yr ($233M) | 233
Domain | $M | % of $900M
Pits & Voids (Domain 4) | 216.5 | 24.1%
Tailings (Domain 2) | 126.4 | 14.0%
Holding Costs (20yr) | 233 | 25.9%
Contingency (35%) | 173 | 19.2%
Infrastructure (Domain 1) | 74.4 | 8.3%
Other domains | 76.7 | 8.5%
Carbon Liability
Decommissioned mine emissions: 4.68M tCO2e over ~20 years
Springbok: 1.6M tCO2e above baseline (5 years)
Brave Blossom: 20.1M tCO2e above baseline (20 years)
Carbon price: $45/t (2026) -> $200/t (2075)
Safeguard Mechanism: >100,000 tCO2e/yr triggers regulation
Workbook Audit: 284 line items, 9 domains, 296 unit rates
0 arithmetic errors — fully verified
8 issues/anomalies identified -> reduction opportunities
Target: all recommendations implementable by end of 2027
Notes: [60s] The $900 million closure estimate breaks down to $494 million in direct works, $173 million contingency at 35%, and $233 million in 20-year holding costs. The workbook is fully audited — zero arithmetic errors — but our review identified 8 issues and anomalies that present reduction opportunities. Carbon liability adds further exposure: 4.68 million tonnes of CO2e over 20 years post-cessation.

## Slide 7
Section 2: Post-Mining Liability Reduction
7
6 SMART Reduction Measures: $180.3M (20%)
$900M -> $719.7M | 6 SMART targets | 20% reduction
# | SMART Target | Saving ($M) | % of $900M | Timeline
1 | Remove duplicate TSF costing (Domain 2) | 39.5-43.8 | 4.4-4.9% | Q2-Q3 2027
2 | Reduce contingency 35%->25% | 49.4 | 5.5% | Q4 2027
3 | House sale vs demolition (505 houses) | 11.8 | 1.3% | 2027-2029
4 | Accelerate progressive rehab ($2.5->$5M/yr) | 11.2 | 1.2% | 2027-2031
5 | Progressive lease relinquishment | ~50 | 5.6% | First app 2035
6 | Monetise gas drainage post-closure | 14.1->rev | 1.6%+ | Q2 2032
 | TOTAL | 180.3 | 20% | 
Implementation Timeline
Q2 2027 TSF removal
Q4 2027 Conting. reduction
2029 House sale
2031 Progress. rehab
Q2 2032 Gas monet.
2035 Lease relinqu.
Before / After
Before: $900M
After: $719.7M
Saving: $180.3M (20%)
S - Specific (line-item-level)
M - Measurable ($180.3M)
A - Achievable (current revenue)
R - Relevant (board objective)
T - Time-bound (end 2027)
Notes: [75s] Our workbook audit identified six SMART-aligned reduction measures totalling $180.3 million — a 20% reduction from the $900 million baseline. The largest is removing a duplicate TSF costing in Domain 2 at up to $43.8 million, followed by reducing contingency from 35% to 25% for $49.4 million. All measures are specific, measurable, achievable, relevant, and time-bound, with implementation timelines starting Q2 2027.

## Slide 8
Section 2: Post-Mining Liability Reduction
8
Carbon Abatement & Gas Monetisation (Rec 3)
Chart: Decommissioned Mine Emissions (4.68M tCO2e over 20 years)
| Unmanaged Emissions | With Abatement (70% reduction) | Residual (30%)
tCO2e (millions) | 4.68 | 3.28 | 1.4
Abatement Approach
1. Extend gas offsite agreement (methane within contract specs)
2. Install post-closure gas capture & flaring infrastructure
3. Generate ACCUs from methane capture/destruction
4. Model Safeguard Mechanism baseline -> abatement pathway
5. Explore flooding sealed workings to suppress emissions
6. Reforestation/vegetation on rehabilitated land
SMART target: 70% reduction vs unmanaged baseline
System operational: Q2 2032 (6 months post-cessation)
Carbon Price Sensitivity
Carbon Price | Unmanaged Liability | With 70% Abatement
$45/t (2026) | ~$211M | ~$63M
$100/t (mid-range) | ~$468M | ~$140M
$200/t (2075 cap) | ~$936M | ~$281M
Cost -> Revenue Conversion
$14.1M gas drainage cost -> revenue stream
ACCU generation from methane destruction
Gas infrastructure required for safety (outburst mitigation)
Incremental cost of post-closure extension is marginal
Dual-purpose investment: safety + revenue
Notes: [60s] Carbon is a growing liability — 4.68 million tonnes over 20 years at prices rising to $200 per tonne. Our third recommendation converts this liability into a revenue stream: extend gas capture post-closure, generate ACCUs from methane destruction, and use bio-sequestration on rehabilitated land. The target is a 70% reduction versus an unmanaged baseline, with the system operational by Q2 2032.

## Slide 9
Section 3: Other Projects & Forward Workplan
9
Other Projects: Brumby, Bronco & Future Exploration
Brumby Open Cut
Xanadu seam, 1.5Mtpa, 25km NE
PFS RECOMMENDED
• 70/30 GCN thermal / PHCC
• Low strip ratio (4.5-4.9 bcm/t historic)
• Cashflow bridge (2031-2033 gap)
• Lower capital than BB; known geological analog
• Gaps: no resource tonnage, no capital estimate
• PFS funding: $5-8M recommended
Bronco Acquisition (Option D)
Adjacent lease ML1654, resource extends from Springbok
MONITOR
• Repeatedly rejected all approaches
• Resource extends from Springbok seam
• Maintain strategic optionality
• Dual-track: monitor + Brumby PFS may strengthen case
• Financial struggles may force future sale
• No resource/quality/strip ratio data available
Future Exploration (Option E)
$5-10M low-cost exploration
PARALLEL WORKSTREAM
• Post-2052 revenue potential
• $900M still due 2031-2050
• Not recommended as standalone
• Include as parallel workstream only
• Does not solve closure timing problem
• Defers revenue too far into future
Notes: [75s] Beyond Brave Blossom, we assessed three alternatives. Brumby Xanadu is a promising open cut concept — lower capital, potential cashflow bridge — but lacks resource tonnage and capital estimates, so we recommend $5-8 million for PFS. Bronco has rejected all approaches; we maintain strategic optionality and monitor their financial position. Future exploration is low-cost but leaves $900 million due with no revenue offset, so it's a parallel workstream only.

## Slide 10
Section 3: Other Projects & Forward Workplan
10
Forward Workplan & Stage Gates
Year | Activity | Capital ($M) | Gate
2027 | PFS, exploration drilling, federal approval engagement, gas contract negotiation | 10 | —
2028 | PFS completion, resource definition, CHPP life extension study, rail/port negotiation | 10 | GATE 1: PFS results
2029 | Ventilation shafts, drift construction, mine infrastructure | 59 | —
2030 | Development continues, approvals finalised, longwall ordered | 84 | GATE 2: Approvals secured
2031 | Mining equipment, ROM bin, conveyors, UG conveyor relocation | 110 | —
2032 | Longwall delivery, CHPP EPCM, ROM bin, commissioning | 221 | GATE 3: First coal
2033+ | CHPP EPCM completion, ramp to full production ~6mtpa | 24 | —
Parallel Workstreams
Closure SMART measures
(6 targets, $180.3M)
Carbon abatement design
(gas capture, ACCUs)
Brumby PFS
($5-8M)
Exploration
($5-10M)
Total forward work plan: $20M before Gate 1 decision | Total capital (direct): $388.9M | Risked (30% cont.): $673.9M Only $20M committed before PFS results and approval pathway are confirmed.
Notes: [60s] The forward workplan is stage-gated to manage risk. We commit $20 million for studies and drilling through 2028, then make a go/no-go decision at Gate 1 based on PFS results and federal approval clarity. Only then does the $369 million development capital flow. Parallel workstreams — closure reduction, carbon abatement, Brumby PFS — run concurrently. First coal is targeted for end 2032.

## Slide 11
Section 4: Go/No-Go Recommendation
11
Option Comparison & Decision Matrix
Option | Capital | Revenue | Closure Impact | Risk | Recommendation
A: Brave Blossom Full Go | $389M | 20yr (2033-52) | $900M deferred 20yr | Medium | RECOMMENDED (stage-gated)
B: No-Go | $0 | None | $900M due 2031-50 | Low (exec) | REJECTED (value destruction)
C: Phased Go | $20M studies | Conditional | Conditional | Low | Incorporated into Rec 1
D: Bronco Acquisition | Unknown | Unknown | Partial deferral | Medium | MONITOR (strategic option)
E: Future Projects Only | $5-10M | Post-2052 | $900M due 2031-50 | Medium | Parallel workstream only
No-Go Impact
$900M closure due
800+ jobs lost
Dustyroo Flats collapse
WM = closure mgmt co.
No revenue offset
Workforce dispersal
Cannot rebuild for future
Decision: GO — Stage-Gated
Combines optionality of C with revenue of A
$20M Stage 1 -> Gate 1 -> Gate 2 -> Gate 3
Major capital only after approvals confirmed
Stage gates protect against binary risks
Federal Approval Fallback
If 25% on MDL fails -> mine only 75% within ML
Mine life: 20yr -> ~15yr (75% of plan)
NPV still strongly positive at ~15yr
75% within ML has state approval already
Early DCCEEW engagement de-risks pathway
Notes: [75s] We evaluated five options. The no-go scenario is explicit: $900 million falls due with no revenue, 800 jobs are lost, and Dustyroo Flats faces economic collapse. Option C — phased go — is incorporated into our Recommendation 1 as stage gates, giving us the optionality of a phased approach with the revenue of a full go. Our decision: go, stage-gated.

## Slide 12
Section 4: Go/No-Go Recommendation
12
Risks & Mitigation per Recommendation
Recommendation | Key Risk | Mitigation | Residual
1. Stage-gated Brave Blossom (NPV $997M, IRR ~52%) | Federal approval uncertainty (25% of mine plan on MDL) | Early DCCEEW engagement (2027) Parallel state/federal process Fallback: 75% within ML = ~15yr | Medium
2. Optimise closure liability ($180.3M / 20% reduction) | Independent review may confirm $900M estimate | Start with highest-confidence item (Duplicate TSF removal, $39.5-43.8M) Phase implementation across 2027 | Low
3. Carbon abatement (70% emissions reduction) | Gas capture infrastructure cost and timeline | Existing drainage infrastructure extends SMART target Q2 2032 achievable ACCU revenue offsets cost | Medium
Cross-Cutting Risks
• Coal quality deterioration — 12% discount may widen; PFS drilling will quantify ($10M in Stage 1)
• Rail/port capacity — 4mtpa current vs 6mtpa needed; 2027 renewal window; 2 competing mines from 2028
• CHPP end-of-life 2032 — $24M EPCM in capital plan; design capacity matches BB ROM target (8Mt/yr feed)
• Labour market — 2 new competing mines from 2028; 2-year gap risk (2031-2033)
Each recommendation has resultant cashflow analysis and implementation risk assessment per brief requirements
Notes: [60s] Each recommendation carries risks we've assessed honestly. The dominant risk is federal approval uncertainty on 25% of Brave Blossom's mine plan — mitigated by early engagement and a fallback to mine only within the ML boundary, reducing life from 20 to 15 years. Closure reduction risk is low — we start with the highest-confidence measure. Carbon abatement leverages existing infrastructure.

## Slide 13
Section 4: Go/No-Go Recommendation
13
Integrated Timeline & Milestones
Year | Brave Blossom | Closure Reduction | Carbon Abatement
2027 | PFS + drilling ($10M) | SMART #1-4 commence | Gas contract negotiation
2028 | Gate 1: PFS results ($10M) | Revised estimate Q4 ($180.3M target) | Abatement design
2029-30 | BB development ($143M) | Progressive rehab accelerated | Brumby PFS ($5-8M)
2031 | Springbok closure; BB equipment ($110M) | Lease relinquishment prep | —
2032 | Gate 3: First coal; Longwall ($221M) | — | Gas capture operational Q2
2033+ | Full production 6mtpa | Lease relinquishment (first app 2035) | Carbon revenue stream
Stage Gates — Major capital gated on study outcomes
Gate 1 (end 2028): PFS results, approval pathway clarity, updated resource -> Go/No-Go decision
Gate 2 (end 2030): Federal approvals secured, CHPP committed, rail/port 6mtpa confirmed
Gate 3 (end 2032): First coal — longwall operational, CHPP EPCM complete, ramp to 6mtpa
Reflects early-stage nature: major capital gated, studies-first approach, $20M committed before Gate 1 decision
Notes: [45s] This integrated timeline shows all three recommendations running in parallel. Studies and closure reduction start immediately in 2027. Gate 1 at end 2028 is our first go/no-go decision. First coal in 2032, gas capture operational by Q2 2032, and progressive lease relinquishment from 2035.

## Slide 14
Closing & Q&A Handover
Summary
3 Recommendations: Stage-gated Brave Blossom | Closure liability reduction | Carbon abatement
Combined NPV: $1,277M | Closure reduction: $180.3M (20%) | Stage 1 ask: $20M
1:2.31 capital-to-liability ratio — $1 invested defers $2.31 of closure
All scenarios positive ($859M-$1,072M); IRR ~52% (well above 8% hurdle)
Key Asks from the Board:
1. Approve $20M studies funding for 2027-2028 (Gate 1 decision end 2028)
2. Endorse closure liability reduction program (6 SMART measures, $180.3M target)
3. Support carbon abatement design and gas contract extension negotiation
4. Note Brumby PFS and Bronco monitoring as parallel workstreams
Appendix slides A1-A6 available for Q&A deep-dives | We welcome your questions
Notes: [60s] To summarise: we recommend proceeding with Brave Blossom through stage gates, reducing closure liability by $180.3 million, and implementing carbon abatement. Combined NPV is $1.28 billion. We ask the board to approve $20 million in studies funding, endorse the closure reduction program, and support carbon abatement design. We welcome your questions.

## Slide 15
APPENDIX
A1
Full Brave Blossom SWOT — All 11 Areas
1. Mine plan & coal quality
S: 20yr life, known measures
W: 12% quality discount, CHPP yield 68%
2. Infrastructure
S: Leverages existing CHPP/rail/port
W: CHPP end-of-life 2032, $24M EPCM
3. Equipment suitability
S: Longwall transferable from Springbok
W: Long lead time 18-24 months
4. Geological / geotechnical
S: Same Blackwater Group stratigraphy
W: Monocline, faulting, historic roof falls
5. Approvals / environmental
S: 75% within ML (state approved)
W: 25% on MDL (federal DCCEEW)
6. Carbon liability
S: Gas drainage infra exists (dual-purpose)
W: 20.1M tCO2e above baseline (20yr)
7. Deliverability / complexity
S: Stage-gated reduces execution risk
W: 6-year development window
8. Financial implications
S: NPV $997M, IRR ~52%, all scenarios +
W: Peak capital $221M in 2032 (gap)
9. Labour supply
S: 800 staff, skills transferable
W: 2 competing mines from 2028
10. People / change mgmt
S: 20yr job security vs contract labour
W: 2yr gap (2031-33), roster changes
11. Other board considerations
S: Community social licence maintained
W: ESG investor sentiment, market perception
Notes: Appendix for Q&A. Full 11-area SWOT from analysis file 02.

## Slide 16
APPENDIX
A2
Workbook Audit: 8 Issues & Anomalies
# | Issue | $ Impact (M) | Confidence | Timeline
1 | Duplicate TSF costing (Domain 2) | 39.5-43.8 | High | Q2-Q3 2027
2 | Contingency at 35% (above industry 25%) | 49.4 | Med-High | Q4 2027
3 | House demolition vs sale (505 houses) | 11.8 | High | 2027-2029
4 | Progressive rehab underfunded ($2.5M vs $5M) | 11.2 | High | 2027-2031
5 | No progressive lease relinquishment plan | ~50 | Medium | First app 2035
6 | Gas drainage not monetised post-closure | 14.1->rev | Medium | Q2 2032
7 | Execution-phase detail missing from workbook | — | — | PFS scope
8 | Outdated rate escalations in rate library | — | — | QS review
Source: 2024 Planned Closure Cost workbook audit (vault files 18-19, analysis file 01). 0 arithmetic errors across 284 line items.
Notes: Appendix for Q&A. Substantiates the $180.3M closure reduction with audit findings.

## Slide 17
APPENDIX
A3
Brave Blossom Capital Schedule (Detailed)
Capital Item | Total ($k) | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033
Projects / Studies | 5,000 | 5 | 5 | 2.5 | 2.5 | — | — | —
Exploration Drilling | 5,000 | 5 | 5 | 2.5 | 2.5 | — | — | —
ROM Bin Upgrade | 15,000 | — | — | — | — | 15 | 7.5 | —
Ventilation Shafts | 20,000 | — | — | 20 | 20 | — | — | —
Mine Infrastructure | 5,000 | — | — | 5 | 5 | — | — | —
Drift | 12,000 | — | — | 12 | 12 | — | — | —
Drift Conveyor | 17,000 | — | — | 17 | 17 | — | — | —
ROM Stockpile | 5,000 | — | — | — | 5 | 5 | — | —
UG Conveyors Relocation | 20,000 | — | — | — | 20 | 20 | — | —
Longwall | 190,000 | — | — | — | — | — | 190 | —
Mining Equipment | 69,900 | — | — | — | — | 69.9 | — | —
Infra + CHPP EPCM | 24,000 | — | — | — | — | — | 24 | 24
TOTAL (direct) | 388,900 | 10 | 10 | 59 | 84 | 110 | 221 | 24
With 30% contingency: $673.9M total | Peak year 2032: $221M (longwall delivery) | Source: vault file 07 / analysis file 01b
Notes: Appendix for Q&A. Full capital breakdown by year and category.

## Slide 18
APPENDIX
A4
Brumby & Bronco SWOT (11 Areas)
Brumby Open Cut (Xanadu seam)
S: Known geological analog, low strip ratio
W: No resource tonnage data
S: Cashflow bridge 2031-2033 gap
W: No capital estimate
S: Lower capital than BB
W: Tenement status unconfirmed
S: 70/30 GCN/PHCC product mix
W: GCN thermal coal (market risk)
O: PFS funding $5-8M
T: 25km from existing infra
O: Extension of known seam
T: Open cut approval complexity
O: Uses existing CHPP (if extended)
T: Competing land use
Bronco Acquisition (Option D)
S: Resource extends from Springbok seam
W: No resource/quality data
S: Adjacent lease (ML1654)
W: Repeatedly rejected approaches
S: Potential synergies with Springbok
W: Unknown capital requirement
S: Maintains workforce continuity
W: Valuation expectations unknown
O: Monitor financial position
T: Acquisition premium risk
O: Dual-track with Brumby PFS
T: Due diligence access limited
O: Future sale may force opportunity
T: Integration complexity
Notes: Appendix for Q&A. Detailed SWOT for alternative projects.

## Slide 19
APPENDIX
A5
No-Go Scenario Deep-Dive (Option B)
Financial Consequences
$900M closure due 2031-2050 (no revenue offset)
$0 revenue post-2031 (Springbok ceases Q4 2031)
Full $900M outflow with no offsetting revenue
CHPP, infrastructure, TLO written off at cessation
20-year unmanaged carbon liability (4.68M tCO2e)
Net cash position 2031-2050: deeply negative
Workforce & Community
800+ jobs lost at cessation (Q4 2031)
Dustyroo Flats economic collapse
Competing mine precedent: media backlash
Supplier chain collapse (diversification happening)
Workforce dispersal — cannot rebuild for future
Native title holder relations if closure mismanaged
NPV Comparison: Go vs No-Go
Scenario | NPV ($M) | Revenue | Closure Impact | Verdict
Go (stage-gated) | 1,277 | $1,652M p.a. (2033-2048) | $900M deferred to post-2052 | Value creation
No-Go (Option B) | 279 (Springbok only) | $0 post-2031 | $900M due 2031-2050 | Value destruction
Notes: Appendix for Q&A. Substantiates the explicit no-go analysis per brief tip #3.

## Slide 20
APPENDIX
A6
Carbon Liability & Safeguard Mechanism Detail
Source | tCO2e | Period | Above Baseline
Springbok operational | 1.6M | 2027-2031 (5yr) | Yes
Brave Blossom operational | 18.9M | 2033-2052 (20yr) | 20.1M tCO2e
Decommissioned mine (combined) | 4.68M | 2052-2072 (20yr) | Yes
Total Scope 1 | 23.6M | — | —
Carbon Price Scenarios
Accelerated Transition: $45/t (2026) -> $200/t (2075)
Modelled in DCF: $12/t (2033) -> $27/t (2050)
Carbon cost in NPV: ~$200M+ over mine life
At $150/t flat: decommissioned liability ~$700M
With 70% abatement: liability reduced to ~$210M
ACCU revenue from methane capture offsets cost
Safeguard Mechanism Baseline
Threshold: >100,000 tCO2e/yr triggers regulation
Springbok baseline: 426k -> 293k tCO2e (2027-2031) — declining hybrid methodology
Brave Blossom baseline: 9,475k -> 0 (2031-2050) — declining over mine life
Above baseline: 20.1M tCO2e over 20 years — material compliance liability
Methodology: NGER Determination Method 3.32 (CH4 emissions from decommissioned mines)
Risk: baseline tightening or methodology changes increase exposure
Mitigation: Recommendation 3 — gas capture, ACCU generation, 70% abatement
Notes: Appendix for Q&A. Full carbon modelling detail. Use for board ESG questions.